## Slide 1
21121 – Active Directory Audit
Status Update
02/04/2022

## Slide 2: AGENDA
Project Status | 
Walkthroughs & Meetings | 
Data Requests | 
Initial Observations | 
Appendix Engagement Details Audit Timeline | 
©2021 CVS Health and/or one of its affiliates: Confidential & Proprietary

## Slide 3: Audit Progress – Current Status
Milestones | Timing* | Status | Comments
Planning Phase |  |  | 
Conduct Kick-Off Meeting | 11/30/21 |  | 
Control Analysis Phase |  |  | 
Conduct Walkthroughs | 12/08/21 |  | 
Validate Risk Control Analysis | 12/31/21 |  | Actual control analysis end date 1/20/22. As a result of the business prioritizing and addressing security issues and ETS organizational changes.
Fieldwork Phase |  |  | 
Testing Execution | 01/31/22 | In Progress | 5 out of 13 controls testing on-going
Reporting Phase |  |  | 
Validation of Findings (if applicable) | 02/04/22 | In Progress | 
Management Action Plan (MAP) | 02/11/22 | On Track | 
Distribute Audit Report | 02/28/22 | On Track | 
*Completion date
The audit is currently in the Testing and Fieldwork Phase.
Audit is expected to be completed on time.  There is one discovery identified at this time.

## Slide 4: Walkthroughs & Meetings
Meeting Schedules | Meeting Schedules |  |  |  | 
# | Meeting Topic | Scheduled Date | Status | Attendees | Notes
1 | Scope and Objective Alignment Meeting | 11/18/2021 | Completed | Mark Ostrowski, Julie Gonzalez, David Kaemmerer, Bianca Moon, Nicole Frazier | IA reviewed the scope and objectives with the AD infrastructure team that were finalized based on the information gathering sessions
2 | AD Management | 11/29/2021 | Completed | Jim Rose, Anne Marie French, Julie Gonzalez, Bianca Moon, Nicole Frazier | Topics covered during the meeting with AD infrastructure team: Policies and Procedures which cover AD management processes Clearly defined roles and responsibilities for AD administration Management reporting of problems, changes, incidents etc.
3 | Secure AD Boundaries | 12/1/2021 | Completed | Jim Rose, Anne Marie French, Julie Gonzalez, Bianca Moon, Nicole Frazier | Topics covered during the meeting with AD infrastructure team: Review AD design and structure (i.e. Domains, Trees, Forests, Organizational Units (OU)) Review Segregation of Duties exists for critical AD functions like Administration, Monitoring, Making Changes etc. Review Domain Trusts relationship
4 | Secure Domain Controller | 12/3/2021 | Completed | Jim Rose, Anne Marie French, Julie Gonzalez, Bianca Moon, Nicole Frazier | Topics covered during the meeting with AD Infrastructure colleagues: Review documented AD Domain Controller installation procedures and processes Availability of Domain Controllers Regular updates of Service Packs Change management procedures associated with AD configurations settings which include Group Policy Objects (GPO) and Organizational Unit management
5 | Administrative Practices | 12/6/2021 | Completed | Jim Rose, Anne Marie French, Julie Gonzalez, Bianca Moon, Nicole Frazier | Topics covered during the meeting with AD infrastructure team: Administrator Account Limitations are based on job responsibilities. Separate accounts for administrative and non-administrative operations
6 | Logging and Monitoring | 12/8/2021 | Completed | Mark Ostrowski, Jim Rose, Anne Marie French, Bianca Moon, Nicole Frazier, Mike Shanahan, Ryan Evans, Ryan Greene, Todd Savoy | Topics covered during the meeting with AD infrastructure team: Evaluate AD Domain Controller Policy and Procedure requirements related to event, activity, logging and review Review AD Domain Controller Monitoring activities for completeness

## Slide 5: Walkthroughs & Meetings
Meeting Schedules | Meeting Schedules |  |  |  | 
# | Meeting Topic | Scheduled Date | Status | Attendees | Notes
7 | Data Request Discussion | 12/20/2021 | Completed | Mark Ostrowski, Jim Rose, Anne Marie French, Bianca Moon, Nicole Frazier | Meeting was scheduled to go over the data request and expectations around due dates for these request were ascertained.
8 | Levels of Admin Rights | 1/4/2022 | Completed | Mark Ostrowski, Jim Rose, Bianca Moon, Nicole Frazier, David Kaemmerer | Meeting was scheduled to understand what other levels of admin rights are configured and who/which team has access to these rights. Conversation followed after UID #13195.
9 | AD Change Management Procedure | 1/10/2022 | Completed | Mark Ostrowski, Bianca Moon, Julie Gonzalez, David Kaemmerer | This meeting was scheduled to better understand the latest modifications (Changes to Domain, Domain controllers, GPOs, OUs) that have occurred in the Active Directory and the change management process executed by the AD infrastructure team.
10 | AD Change Management Discussion- Follow up | 1/14/2022 | Completed | Mark Ostrowski, Bianca Moon, Julie Gonzalez, David Kaemmerer | This meeting was scheduled to discuss if there was an easier way to determine samples to test the change management procedures
11 | Follow up Questions | 1/20/2022 | Completed | Mark Ostrowski, Bianca Moon, Julie Gonzalez, David Kaemmerer | The meeting was scheduled to go over several follow up questions which would help us document the test procedures of several control areas.
12 | Domain Trust Relationship – Follow up | 1/21/2022 | Completed | Jim Rose, Mark Ostrowski, Nicole Frazxier, Bianca Moon, Julie Gonzalez, | This meeting was scheduled to go over the Domain Trust relationships and better understand how two way and one way domain trust relationships are established leveraging the AD Domain Trust diagram.
13 | Administrative Accounts :UID 14834 | 1/27/2022 | Completed | Jim Rose | Jim performed a screenshare session to provide us with the required screenshots in order to complete testing and document Control D.1
14 | AD Change Management Data Request | 1/28/2022 | Completed | Jim Rose | This meeting was scheduled to go over in detail the change management procedures carried out by the AD Infrastructure team.
15 | DC Advanced Audit Settings Discussion | 2/3/2022 | Completed | Ann Marie French, James Rose, Nicole Frazier, David Kaemmerer | Meeting is scheduled to discuss the Domain Controller Advanced Audit settings for the 10 configuration settings showing (no auditing) and as a result do not provide the AD team with relevant alerts.
16 | AD High Privileged Users | 2/3/2022 | Completed | Brad Abreu, James Rose, Nicole Frazier, David Kaemmerer, Bianca Moon | Meeting was scheduled to discuss the PARs performed for AD High Privelege User Groups.

## Slide 6: Data Requests As of 5 PM ET on 2/3
Data Requests |  |  |  |  |  |  | 
# | UID | Title | Started On | Due (Date) | Status | Preparer(s) | Notes
01 | 13200 | Walkthroughs and Related Documentation (Logging and Monitoring) | 12/15/2021 | 12/21/2021 | Closed | Jim Rose | 
02 | 13730 | AD Management - Monthly AD Stat Sheet | 12/21/2021 | 12/22/2021 | Closed | Jim Rose | 
03 | 14251 | Secure AD Boundaries - Architectural Diagram | 12/21/2021 | 12/22/2021 | Closed | Jim Rose | 
04 | 13195 | Admin Access | 12/15/2021 | 12/23/2021 | Closed | Jim Rose | 
05 | 13206 | Security of Domain Controllers- Comm / Decomm of DC | 12/16/2021 | 12/23/2021 | Closed | Jim Rose | 
06 | 13216 | AD Administrative Practices - Admin Functions | 12/17/2021 | 12/23/2021 | Closed | Jim Rose | 
07 | 13199 | Security of Domain Controllers: DC Redundancy | 12/16/2021 | 12/29/2021 | Closed | Jim Rose | 
08 | 13732 | System Downtime/Outage | 12/21/2021 | 12/29/2021 | Closed | Jim Rose | 
09 | 14252 | Secure AD Boundaries - Domain Trust Relationship | 12/21/2021 | 12/29/2021 | Closed | Jim Rose | 
10 | 14266 | Secure AD Boundaries - Domain Trust Relationship (Follow-Up) | 12/27/2021 | 1/3/2022 | Closed | Jim Rose | 

## Slide 7: Data Requests As of 5 PM ET on 2/3
Data Requests |  |  |  |  |  |  | 
# | UID | Title | Started On | Due (Date) | Status | Preparer(s) | Notes
11 | 13731 | AD Management - Reporting Metrics | 12/20/2021 | 1/7/2022 | Closed | Jim Rose | 
12 | 14374 | A1.2 - Access to Active Directory | 1/4/2022 | 1/7/2022 | Closed | Jim Rose | 
13 | 14375 | B1.2 Domain Trust Relationship | 1/4/2022 | 1/7/2022 | Closed | Jim Rose | 
14 | 14381 | C1.3 - Change Management Procedures | 1/6/2022 | 1/11/2022 | Closed | Jim Rose | 
15 | 14365 | C1.2 - Patch Updates | 1/7/2022 | 1/12/2022 | Closed | Jim Rose | 
16 | 14721 | A1.1 Standard Operating Procedures | 1/10/2022 | 1/12/20220 | Closed | Jim Rose | 
17 | 14776 | C1.2 - Patch Updates - Samples | 1/10/2022 | 1/13/2022 | Closed | Jim Rose | 
18 | 14777 | C1.1 - Domain Controller Availability (Follow Up) | 1/10/2022 | 1/13/2022 | Closed | Mark Ostrowski | 
19 | 14782 | B1.2 Domain Trust Relationship (Follow Up) | 1/10/2022 | 1/13/2022 | Closed | Mark Ostrowski | 

## Slide 8: Data Requests As of 5 PM ET on 2/3
Data Requests |  |  |  |  |  |  | 
# | UID | Title | Started On | Due (Date) | Status | Preparer(s) | Notes
20 | 14784 | C1.3 – Change Management – Splunk Log Request | 1/21/2022 | 1/24/2022 | Closed | Mark Ostrowski | 
21 | 14800 | C1.3 – Change Management Procedures | 1/18/2022 | 1/20/2022 | Closed | Ann French | 
22 | 14834 | D1.1 – Administrative Accounts | 1/21/2022 | 1/25/2022 | Closed | Mark Ostrowski | 
23 | 14854 | B1.3 – Segregation of Duties | 1/25/2022 | 1/27/2022 | Closed | Jim Rose | 
24 | 14856 | Active Directory Trusts | 1/24/2022 | 1/26/2022 | Closed | Jim Rose | 
25 | 14857 | E2.1 Administrative Activity Logging and Monitoring | 1/24/2022 | 2/4/2022 | Open | Jim Rose | 
26 | 15122 | C1.3 - Trust Removal System Log | 1/28/2022 | 1/28/2022 | Open | Jim Rose | 
27 | 15123 | C1.3 - SOC Alerts for Admin Activity | 1/28/2022 | 1/31/2022 | Closed | Jim Rose | 
28 | 15125 | C1.3 - Server Logs for Sample DCs | 1/28/2022 | 1/31/2022 | Closed | Jim Rose | 
29 | 15133 | E2.2 SCOM Event Logs | 1/28/2022 | 1/31/2022 | Closed | Jim Rose | 
30 | 15135 | E2.2 Event Monitoring | 1/31/2022 | 2/1/2022 | Closed | Jim Rose | 
31 | 15416 | E2.2 SCOM Alerts Follow Up | 2/3/2022 | 2/3/2022 | Open | Jim Rose | 

## Slide 9: Potential Discovery Identified The following discoveries were identified and will be discussed with applicable business owners to ensure alignment. These are considered draft and subject to change until the final report is issued.
Initial Discovery | Initial Discovery |  | 
# | Discovery | IA Comment /Recommendation | Business Comment
1 | IA requested standard operating procedures for critical Active Directory functions such as commissioning and decommissioning domains/domain controllers, managing Group Policy Objects (GPOs) and change management. IA noted the AD Team utilizes the standard Change Management standards/procedures CITD-0020 and CITD-0021 to manage AD infrastructure changes and have developed an SOP to support the commissioning and decommissioning of domains/domain controllers, however an SOP to provide guidance and management over GPOs does not exist. SOPs are critical in providing direction to the team members for the steps and procedures to follow while performing day to day responsibilities. Without proper governance in place there is lack of accountability and ownership for problem resolution resulting in adverse service delivery. | IA recommends Active Directory team formalize the existing SOPs by adding information regarding relevant stakeholders, document owner, revision history and evidence of sign offs and document guidance around managing GPOs. Additionally, IA recommends creation of a new SOP document with steps and procedures to follow while managing and handling support calls when an event / outage is identified | 

## Slide 10: Remaining Project Schedule
Project Schedule |  |  | 
Step | Description | Expected Date | Status
1 | Phase I – Planning and Scoping Kick Off Meeting | November 2021 | Completed
2 | Phase II – Control Analysis Walkthrough Interviews & Control Validation | December 2021 | Completed
3 | Phase III – Fieldwork and Testing Data Analysis & Test Execution | January 2022 | In Progress
4 | Phase IV – Reporting Audit Report | February 2022 | In Progress
©2021 CVS Health and/or one of its affiliates: Confidential & Proprietary

## Slide 11
Appendix

## Slide 12: Engagement Details Objectives & Inherent Risks
Objective Area | Related Inherent Risk* | Key Areas of Focus
AD Management | AD infrastructure is not managed effectively which could result in lack of accountability and ownership for problem resolution resulting in adverse service delivery. | Policies and Procedures which cover AD management processes Clearly defined roles and responsibilities for AD administration Management reporting of problems, changes, incidents etc.
Secure AD Boundaries | AD boundaries are not clearly defined which may lack security controls and may introduction vulnerability threats. | Review AD design and structure (i.e. Domains, Trees, Forests, Organizational Units (OU)) Review Segregation of Duties exists for critical AD functions like Administration, Monitoring, Making Changes etc. Review Domain Trusts relationship
Secure Domain Controllers | Failure to secure the enterprise Domain Controllers may result in exposure to security threats through unauthorized system access. | Review documented AD Domain Controller installation procedures and processes Availability of Domain Controllers Regular updates of Service Packs Change management procedures associated with AD configurations settings which include Group Policy Objects (GPO) and Organizational Unit management
*Reflects the level of risk that exists in the absence of controls
Note: While the audit will focus on the objectives listed above, IA has a responsibility to assess any additional risks identified during the audit, and report any issues identified. Where applicable, issues will also be evaluated against requirements for Sarbanes-Oxley or other regulatory standards.

## Slide 13: Engagement Details Objectives & Inherent Risks
Objective Area | Related Inherent Risk* | Key Areas of Focus
AD Administrative Practices | Administrative practices are not consistently followed which may impact AD operations. | Administrator Account Limitations are based on job responsibilities. Separate accounts for administrative and non-administrative operations
Logging and Monitoring | Logging settings not aligned with company requirements may result in critical AD operation activities not captured for management review. | Evaluate AD Domain Controller Policy and Procedure requirements related to event, activity, logging and review Review AD Domain Controller Monitoring activities for completeness
*Reflects the level of risk that exists in the absence of controls
Note: While the audit will focus on the objectives listed above, IA has a responsibility to assess any additional risks identified during the audit, and report any issues identified. Where applicable, issues will also be evaluated against requirements for Sarbanes-Oxley or other regulatory standards.

## Slide 14
Kick-off and
information gathering
Week 1
Information gathering, identification of relevant stakeholders
November 18, 2021
Kick-off call
Reporting
Weeks 10-13
Finalization of observations, and stakeholder alignment
Preliminary report, exit meetings
February 28, 2022
Issuance of final report
Fieldwork and walkthroughs
Weeks 2-9
Conduct process and controls walk-throughs, interviews, and initial analysis
December 2021 - January 2022
Planning and scoping
Preparation for kick-off
Hold planning meetings and draft initial scope and approach
November 2021
Audit Timeline