## Slide 1: 21115 – Enterprise Person Hub (EPH) Status Update
11/25/2021

## Slide 2: AGENDA
Project Status | 
Walkthroughs & Meetings | 
Data Requests | 
Initial Discoveries | 
Appendix | 
©2021 CVS Health and/or one of its affiliates: Confidential & Proprietary

## Slide 3: Audit Progress – Current Status
The audit is currently in the Testing Phase.
Audit is expected to be completed on time. There are no discoveries identified at this time.
Milestones | Timing* | Status | Comments
Planning Phase |  |  | 
Perform Initial Walkthroughs | November 2021 | Complete | 
Validate Risk Control Analysis | November 2021 | Complete | 
Testing Phase |  |  | 
Testing Execution | December 2021 | In Progress | 11 out of 11 tests in progress.
Reporting Phase |  |  | 
Validation of Discoveries (if applicable) | January 2022 | On Track | 
Management Action Plan (MAP) (if applicable) | January 2022 | On Track | 
Distribute Audit Report | January 2022 | On Track | 
*Completion date

## Slide 4: Walkthroughs & Meetings
 | Meeting Schedules |  |  |  | 
 | Meeting Topic | Attendees | Scheduled Date | Status | Notes
1 | CVS ID Walkthrough | Seun Mafi, Nazare Jason, Vazquez Sol, Monika Godara, Tyrell Jarett, Terri Ann G Quiambao, Joseph Rocha, Wijendran Nadesan, N Nijesh, Ron Ronald J, Carmen Malangone, David Dessommes | 10/25/2021 | Complete | 
2 | Data Integrity Walkthrough | Seun Mafi, Jason Nazare, Monika Godara, Roy Ronald J, Carmen Malangone, David Dessommes, Nadesan Wijendran, N Nijesh, Sol Vazquez, Tyrell Jarrett, Joseph Rocha, Terri Ann G Quiambao, Sourabh Mayya | 10/28/2021 | Complete | 
3 | Access Management Walkthrough | Seun Mafi, Monika Godara, Ronald J Roy, Carmen Malangone, David Dessommes, Nadesan Wijendran, N Nijesh, Sol Vazquez, Jason Nazare, Tyrell M Jarrett, Joseph Rocha, Terri Ann G Quiambao | 11/1/2021 | Complete | 
4 | Data Protection Walkthrough | Seun Mafi, Monika Godara, Nadesan Wijendran, N Nijesh, Sol Vazquez, Jason Nazare, Tyrell Jarett, Joseph Rocha, Terri Ann G Quiambao, Ronald J Roy, Carmen Malangone, David Dessommes | 11/2/2021 | Complete | 
5 | Scalability and Availability Walkthrough | Seun Mafi, Wijendran Nadesan, N Nijesh, Sol Vazquez, Jason Nazare, Tyrell M Jarett, Joseph Rocha, Terri Ann G Quiambao, Ronald J Roy, Carmen Malangone, David Dessommes | 11/5/2021 | Complete | 
6 | Follow up -Data Protection | Monika Godara, Nadesan Wijendran, N Nijesh, Sol Vazquez, Seun Mafi, Tyrell Jarett, Joseph Rocha, Terri Ann G Quiambao, Ronald J Roy, Carmen Malangone, David Dessommes | 11/8/2021 | Complete | 
7 | Follow Up- Access Management- Logging and Monitoring | Monika Godara, Nadesan Wijendran, N Nijesh, Sol Vazquez, Seun Mafi, Tyrell Jarett, Joseph Rocha, Terri Ann G Quiambao, Ronald J Roy, Carmen Malangone, David Dessommes | 11/18/2021 | Complete | 
8 | Duplicate Management Walkthrough | Tyrell Jarrett, Sol Vazquez, Seun Mafi, David Dessommes, Nadesan Wijendran Carmen Malangone | 11/19/2021 | Complete | 

## Slide 5: Walkthroughs & Meetings
 | Meeting Schedules |  |  |  | 
 | Meeting Topic | Attendees | Scheduled Date | Status | Notes
9 | QL Periodic Sync Process | N Nijesh, Monika Godara, Carmen Malangone, Sol Vazquez, Nadesan Wijendran, Seun Mafi | 11/23/2021 | Complete | Follow up meeting was conducted to get clarity on data request received for B.2 – Successful Adds reconciliation control
2 | Data Request Validation | Joseph Rocha, Monika Godara, N Nijesh, Sol Vazquez, Nadesan Wijendran | 12/01/2021 | Scheduled | Follow up meeting scheduled to go over data request received for Data Protection

## Slide 6: Data Requests – as of 12:00 PM ET on 11/18
 | Data Requests |  |  |  |  |  | 
# | UID | Title | Request Date | Due Date | Status | Preparers | Notes
1 | 12821 | D.1, D.2 – Data Protection | 11/12/2021 | 11/30/2021 | Open | Nadesan Wijendran | 
2 | Email | C.1- User Access Management- UAL | 11/15/2021 | 11/22/2021 | Closed | Nadesan Wijendran | 
3 | 12884 | A.1 - CVS ID Creation Management | 11/17/2021 | 11/19/2021 | Closed | Nadesan Wijendran | 
4 | 12886 | C.1 - User Access Provisioning | 11/17/2021 | 11/19/2021 | Closed | Nadesan Wijendran | 
5 | 12892 | E.1 – System Performance: Alert Thresholds/Configurations | 11/17/2021 | 11/19/2021 | Closed | Nadesan Wijendran | 
6 | 12893 | E.2 Event Monitoring: Quarterly and Monthly Reports | 11/17/2021 | 11/19/2021 | Open | Nadesan Wijendran | 
7 | 12897 | B.1 – Completeness Validation Checks | 11/18/2021 | 11/192021 | Closed | Nadesan Wijendran | 
8 | 12898 | B.2 – Successful Adds Reconciliation | 11/18/2021 | 11/29/2021 | Open | Nadesan Wijendran | During QL Periodic Sync Process meeting, IA obtained assurance that additional data will be provided
9 | 12959 | CVS ID Creation | 11/18/2021 | 11/22/2021 | Closed | Nijesh Narayanankutty | 
10 | 12982 | E.1 0 System Performance (Scalability): SLAs and Remediation (For Alerts) | 11/18/2021 | 11/29/2021 | Certified | Nijesh Narayanankutty | 

## Slide 7: Data Requests – as of 12:00 PM ET on 11/18
 | Data Requests |  |  |  |  |  | 
# | UID | Title | Request Date | Due Date | Status | Preparers | Notes
11 | 12983 | E.2 Capacity Planning (Availability): Quarterly Review Communications | 11/22/2021 | 11/29/2021 | Open | Nijesh Narayanankutty | 
12 | 12984 | E.2 – Capacity Planning (Availability) Capacity Increase Test Plans | 11/22/2021 | 11/29/2021 | Open | Nijesh Narayanankutty | 
3 | 13001 | A.1 – CVS ID Creation Management | 11/22/2021 | 11/30/2021 | Open | Nijesh Narayanankutty | 

## Slide 8: Discoveries Identified The following discoveries were identified and will be discussed with applicable business owners to ensure alignment. These are considered draft and subject to change until the final report is issued.
No. | Initial Discoveries
1 | 

## Slide 9: Appendix

## Slide 10: Audit Timeline
Kick-off and information gathering
Week 1
Information gathering, identification of relevant stakeholders
October 20th, 2021
Kick-off call
Reporting
Weeks 10 – 12
Finalization of observations, and stakeholder alignment
Preliminary report, exit meetings
January 2022
Issuance of final report
Field-work and walk-throughs
Weeks 2 – 9
Conduct process and controls walk-throughs, interviews, and initial analysis
November – December 2021
Planning and scoping
Preparation for kick-off
Hold planning meetings and draft initial scope and approach
10
Notes: Introducing Audit Timeline Visual Display

## Slide 11: Audit Scope
To validate that controls are designed effectively to ensure demographic data is governed, secured, complete, and accurately maintained within Enterprise Person Hub.
Audit Objective
Controls are in place to ensure ID creation is managed adequately.
Data integrity controls are in place to ensure data entering EPH is complete and accurate.
Access controls are in place to ensure access to the database is appropriately managed by authorized individuals
Data protection controls are in place to ensure data is secured in transit and at rest
Scalability and availability controls are in place to support large volumes of data
Estimated Completion Date: January 2022

## Slide 12: Engagement Details Objectives & Inherent Risks
Objective Area | Related Inherent Risk* | Key Areas of Focus
Controls are in place to ensure ID creation is managed adequately. | CVS IDs may unintentionally be created, updated, or deleted resulting in erroneous data in EPH. | CVS IDs are created, updated/edited, and deleted completely and accurately, and to ensure duplicates do not exist
Data integrity controls are in place to ensure data entering EPH is complete and accurate. | Data integrity and daily balance controls between the source systems and EPH are not in place and the data does not reconcile for completeness and accuracy | Data validation checks are performed between the source systems and EPH Data integrity alerts are communicated and remediated timely per defined SLAs
Access controls are in place to ensure access to the database is appropriately managed by authorized individuals | Access to the database may not be adequately restricted or monitored, resulting in unauthorized access and changes | Access to IBM MDM is restricted adequately Provisioning Recertification Access activities are logged and monitored
*Reflects the level of risk that exists in the absence of controls

## Slide 13: Engagement Details Objectives & Inherent Risks
Objective Area | Related Inherent Risk* | Key Areas of Focus
Data protection controls are in place to ensure data is secured in transit and at rest | Data in transit and at rest is not secure to prevent unauthorized access to confidential, proprietary, or otherwise sensitive data | Ensure data in transit and data at rest is encrypted in accordance with company standards Encryption/masking methods are used for protecting data stored in IBM MDM Encryption methods are in place for data in transit
Scalability and availability controls are in place to support large volumes of data | Technology infrastructure supporting EPH is unable to support large volumes of data | EPH is measured and monitored to ensure the technology infrastructure is scalable to support large volumes data
*Reflects the level of risk that exists in the absence of controls