## Slide 1: 21170 – SimpleDose Application (SDA) Kick-off Meeting
    April 8, 2021

## Slide 2
Engagement Details
Key Milestones
Key Contacts
Expectations
Next Steps
Appendix
  Standard Terminology
  Escalation Protocol
  Patient Safety Work Product Protocols
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”

## Slide 3: Engagement Details Executive Summary
CVS Health (the “Company”) launched the SimpleDose Application (“SDA” formerly Multi-Dose Packaging(MDP)) in an effort to simplify the daily routine of retail pharmacy patients taking multiple medications. SDA provides patients with a 30-day supply of pre-sorted medications in easy-to-open packets, which are labeled by dose, date, and time, and delivered directly to the patient’s home or local CVS Pharmacy, at no added cost. Patients may enroll by calling the Pharmacy Care Team, directly online, and in select instances, in-store with the Retail Pharmacy Team.
The SDA is undergoing systematic enhancements to support the company’s growth strategy and help meet the goal of 70 million prescriptions in 2022. Enhancements including the automation of patient enrollment will continue to improve workflow, increase efficiencies in processing and shipping orders, reduce labor costs, and communication with patients. SDA is currently in pilot phase with about 10% deployment of new patients into the platform with plans to increase its patient capacity up through July 2021 whereby all patients would have been enrolled on the platform.
At the request of management, Internal Audit (IA) will perform an application review to assess the effectiveness of the controls in place for SDA. In addition, IA will participate in status meetings with the SDA Program Leadership to understand timelines, deficiencies, and other project status milestones. Furthermore, IA will communicate observations, if there are any identified as a part of this review, to process owners on a real time basis to ensure timely closure.
Audit Scope: Validate that the newly developed Simple Dose application controls are designed and operating effectively.
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”

## Slide 4: Engagement Details Objectives & Inherent Risks
Objective Area | Related Inherent Risk* | Key Areas of Focus
Capacity Planning | Technology infrastructure supporting the SimpleDose application is unable to support increased Patient and Pharmacy data volume. | SimpleDose is measured and monitored to ensure the technology infrastructure is scalable to support large volume of Patient and Pharmacy data.
User Access | Access to critical system files is not restricted or monitored based on individual job responsibilities. | Validate that access to critical SimpleDose system files are restricted based on the individual’s job responsibilities.
Change Management | Changes to the production environment are not reviewed, tested, or approved prior to production implementation. | Ensure changes to critical SimpleDose system files are appropriately documented, tested, and approved prior to deployment. Review change management controls and processes for new/modified SimpleDose components introduced as part of Phase 1 (R1.1 & R1.2). Identified defects are addressed prior to production implementation. Confirm servers supporting the SimpleDose Application are scanned for vulnerabilities. Vulnerabilities identified are addressed in accordance with corporate policy and procedure.
*Reflects the level of risk that exists in the absence of controls
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”

## Slide 5: Engagement Details Objectives & Inherent Risks
Objective Area | Related Inherent Risk* | Key Areas of Focus
Data Integrity | Data integrity and daily balance controls between the source systems and SDA are not in place and data does not reconcile completely and accurately. | Evaluate data integrity and periodic balance controls to ensure the completeness and accuracy of data ingested into the environment. Monitoring and remediating system alert and failures.
Application Processing | Without a controlled process for running jobs and for altering job schedules, unauthorized programs could be executed that impact patient information and/or the distribution of pharmaceutical products. | Validate that the ability to create, modify, and delete job schedules are restricted to authorized personnel.
Application Resiliency | Failure to adequately configure, resolve backup failures, and ensure data can be restored could result in the inability to recover significant Retail Pharmacy systems. | Confirm data backup & restoration efforts are performed and documented for the SimpleDose application based on the Disaster Recovery tier ranking. Confirm backups are configured Review backup schedules and logs Backup failures are addressed
*Reflects the level of risk that exists in the absence of controls
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”

## Slide 6: Engagement Details Business Input
Input required from the Business
Recent changes in process or organization
  Various sub-processes or multiple locations
  Any internal/external reviews (e.g. consulting, external audit, process reengineering)
Limitations in resources or process
Existing issues
Other concerns
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”

## Slide 7: Key Milestones
Audit Milestone | Estimated Completion Date
Planning & Scoping Phase Hold planning and scoping meetings with the Business Area(s) Finalize the scope and objectives of the audit Draft Kick-Off Deck and hold kick-off meeting (if applicable) to discuss audit project and scope | March 2021
Control Analysis Phase Conduct walkthrough meetings Document process understanding Document risks and controls Obtain management alignment with our understanding of the process and controls Design audit test plan | April 2021
Fieldwork & Testing Phase Execute audit test plan Keep management aware of findings as they are identified Validate testing executions with IA management | May 2021
Reporting Phase Obtain management alignment with audit issues Obtain management action plans to address audit issues Draft audit report based on testing findings Hold close meeting (if applicable) to discuss draft audit report with management Obtain alignment with final report before distribution | June 2021
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”

## Slide 8: Key Contacts Internal Audit & Business Area
Internal Audit Team |  | 
Role | Name | Responsibilities
Audit Director(s) | Lynn Atkin Ronald Roy | Oversight/guidance and liaison with Business Owners
Audit Manager | Sarah Kubiak | Oversight/guidance and liaison with Business Owners
Lead Auditor | Michael Bavasso | Liaison with Business Owners, develop project plan and lead team
Staff Auditor(s) | Daniel Benner Seun Mafi Ashish Joshi | Liaison with Business Owners, controls analysis and test execution
Business Line Contacts |  | 
Role | Name | Responsibilities
Primary POC Executive Management | Ray Auger | Primary Business Owner (VP Level or Above)
Primary POC | Gaurav Sachdeva William Mullins Padmalatha Ajit | Transfer knowledge of key business functions, process documentation and key control evidence to the Internal Audit team; control validation and issue ownership.
Key Business Line Contacts listed are a starting point for discussion and not meant to indicate these individuals are responsible for the process, observations and/or report.
Legal Contacts |  | 
Role | Name | Responsibilities
Legal Representative | Jennifer Schneider | Designated in-house attorney for projects performed under the Patient Safety Work Product privilege
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”

## Slide 9
Engagement Details Business Input
Input required from the Business
Recent changes in process or organization
  Various sub-processes or multiple locations
  Any internal/external reviews (e.g. consulting, external audit, process reengineering)
Limitations in resources or process
Existing issues
Other concerns
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”

## Slide 10
Expectations Internal Audit & Business Line
What you can expect from Internal Audit:
Prompt notification of concerns, such as audit issues or roadblocks
Potential unfamiliarity with business process
Focus on key areas of high risk
Ongoing communication throughout the project
Travel to primary location(s), as necessary
Draft Audit Report will be provided for the business’ review at least 24 hours in advance of the close meeting
What Internal Audit expects from your Team:
Awareness and engagement
All relevant documentation, including process/control documentation, policies & procedures, key reporting and dependencies be provided promptly during the planning phase
Management and staff will make reasonable time available for interviews, provide prompt responses to follow-up questions and deliver requested support or information by agreed upon due dates
All layers of management in your Team’s organization are kept informed of identified exceptions and issues
Management will review the Draft Audit Report in advance of the close meeting to allow for a more targeted discussion
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”

## Slide 11
Additional Information to Consider
AuditBoard is the audit management tool used by Internal Audit
  Internal Audit may leverage this system for the following aspects of the project:
    Centrally manage and communicate requests
    Gain alignment with verbiage of Findings and Observations
      Request Management’s Remediation Plan for inclusion within the Audit Report
    Management of Findings upon the conclusion of the audit
    Note: Please do not upload any PII / PHI to AuditBoard; please discuss with Internal Audit the most appropriate means to transmit any sensitive documentation requested as part of this project
Audit Surveys will be sent at the conclusion of the audit to the relevant business contacts
  Audit Surveys help Internal Audit aggregate feedback on what went well during the project and areas of opportunity for the team to reflect on going forward
    Survey will be deployed from AuditBoard typically within 1-2 weeks of report issuance
    Results are gathered centrally by our Department administrative team and feedback is anonymously provided back to the respective Internal Audit team
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”

## Slide 12
Next Steps
Alignment with project scope from the business
Issuance of Kick-Off deck to formalize kick-off of the project
Schedule walkthrough meetings with relevant business contacts
Schedule periodic status meetings with the business to keep open line of communication
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”

## Slide 13: Appendix

## Slide 14
Standard Terminology Overall Control Environment Opinion
Effective | Overall, controls are appropriately designed and functioning as intended. Control weaknesses, if noted, do not threaten the effectiveness of the process reviewed.
Mostly Effective | Except for the issues noted, controls in place provide reasonable assurance that business risks are adequately mitigated.
Improvement Needed | One or more significant control weaknesses exist that require prompt action to prevent the process from becoming ineffective.
Ineffective | Control weaknesses are pervasive or one weakness is so severe that it impacts the entire operation under review. Immediate management attention is needed to remediate the issue identified.
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”

## Slide 15
Standard Terminology Ratings & Management Action Plan
The rating of findings drives the timing of remediation and also the level of management that is responsible for developing and implementing action plans.
High | The identified risk requires the immediate attention of department and senior management to prevent the process from becoming ineffective, and an agreed-upon action plan for resolution is needed.
Medium | The identified risk requires the near-term attention of the responsible manager. There should be an agreed-upon action plan for its resolution.
Low | The identified risk does not warrant immediate attention; however, there should be an agreed-upon action plan for ultimate resolution.
Deficiency | If SOX related, rating categories will be assessed as Deficiency, Significant Deficiency, or Material Weakness. Note: While the audit will focus on the objectives previously noted, IA has a responsibility to assess any additional risks identified during the audit, and report any issues identified. Where applicable, issues will also be evaluated against requirements for Sarbanes-Oxley or other regulatory standards.
Each Management Action Plan requires a remediation due date which is tracked by IA.
Remediation Due Date | Reflects the time required for Management to complete the agreed upon action plan, as well as time for IA to complete the associated validation procedures to ensure the action plan has been implemented effectively.
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”

## Slide 16
Escalation Protocol
Potential Causes for Escalation
Data requests not received within expected timeframes
Data provided does not align with follow-up requests for clarification
Key attendees miss walkthrough meetings following confirmed schedules
Internal Audit is denied access to key data or people that may impact findings
Management accepts a level of residual risk not acceptable to the organization
Management is not aligned with identified issues, risk priority ratings and/or the overall audit opinion
Escalation Process – when one or more of the above events occur
Convey the issue to the next level of management
The responsible SVP / VP may be notified of causes which delay audit execution
Escalations may be tracked and reported during recurring status meetings with management
The CAE may discuss with Senior Management and the Audit Committee, if necessary
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”

## Slide 17: Patient Safety Work Product (PSWP) Protocol
Internal Audit conducts reviews of activities performed by CVS business unit providers (“CVS Providers”). Certain reviews conducted by Internal Audit could improve patient safety and/or the quality of health care delivery by the respective CVS Provider. Those reviews, referred to herein as “Patient Safety Internal Audits,” are conducted in accordance with, and subject to the protections of, the Patient Safety and Quality Improvement Act of 2005. The information developed and/or assembled in a Patient Safety Internal Audit is confidential and privileged patient safety work product (“PSWP”).
Portions of the audit process, including reporting, are enhanced to ensure the project is appropriately protected as PSWP:
  Designated in-house attorney reviews the Kick-Off deck prior to distribution and is invited to the Kick-Off meeting and other applicable status meetings
  The PSWP Label (“PRIVILEGED & CONFIDENTIAL: PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”) is added to all deliverables, meeting invites and other communications
  Designated in-house attorney is copied on all communications relating to conclusions, findings and action plans
  Deliverables, including the Kick-Off deck and Audit Report, should not be forwarded to any colleagues outside of the distribution list and if responding to the distribution of the Kick-Off deck or Audit Report, the designated attorney should be copied
  Audit Reports and Memos include predefined language to support the PSWP privilege

## Slide 19: Distribution List
Compliance
Eric Cartier Tom Pawlik
Internal Audit
Lynn Atkin Michael Bavasso Daniel Benner David Horst Ashish Joshi Sarah Kubiak Seun Mafi Ronald Roy
IT Retail Systems
Padmalatha Ajit Ray Auger William Mullins Gaurav Sachdeva Jeanne Willis
Legal
Rachel Caldwell Flossie Crisp Jennifer Schneider
© 2021 CVS Health and/or its affiliates. Confidential and proprietary.
“PRIVILEGED AND CONFIDENTIAL PATIENT SAFETY WORK PRODUCT UNDER FEDERAL LAW”