## Slide 1
20335 – Benefits Production Access
Status Report:
03/31/2021

## Slide 2: AGENDA
Project Status | 
Walkthroughs & Meetings | 
Data Requests | 
Initial Observations | 
Appendix | 
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”

## Slide 3: Project Status
As of 03/31/2021
Planning and Scoping Phase – Complete ​ Control Analysis Phase – In Progress Fieldwork Phase – In Progress Reporting Phase – Not Started
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”

## Slide 4: Walkthroughs & Meetings
 | Meeting Schedules |  |  |  |  | 
 | Meeting Topic | Scheduled Date | Completed Date | Follow up Date | Completed Date | Notes
1 | Benefits Production Access Review – Background (Green Screen Demo) | 02/05/2021 | 02/05/2021 |  |  | https://cvshealth.auditboardapp.com/download?file_id=77650&name=Benefits%20Production%20Access%20Narrative%20(Feb%205)%20-%20IT.docx
2 | Manual Claims – Access Discussion | 02/12/2021 | 02/12/2021 |  |  | 
3 | Benefits Production Access Review | 02/22/2021 | 02/22/2021 |  |  | 
4 | Auditboard Walkthrough | 02/24/2021 | 02/24/2021 |  |  | 
5 | EzTest Tool Walkthrough | 03/18/2021 | 03/18/2021 |  |  | https://cvshealth.auditboardapp.com/download?file_id=76081&name=EZTest%20tool%20Walkthrough.docx https://cvshealth.auditboardapp.com/download?file_id=76275&name=Meeting%20Minutes%20-%20EzTest%20Tool%20Walkthrough%20(March%2018%202021).docx
6 | DA Brainstorming | 03/22/2021 | 03/22/2021 |  |  | https://cvshealth.auditboardapp.com/download?file_id=77652&name=DA%20Brainstorming%20(March%2022%202021).docx
7 | DA Brainstorming – IT | 03/26/2021 | 03/26/2021 |  |  | https://cvshealth.auditboardapp.com/download?file_id=77651&name=Meeting%20with%20DA%20Team%20(March%2026%202021).docx
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”

## Slide 5: Open Data Requests – as of 03/31/2021
 | Data Requests |  |  |  |  |  |  | 
# | UID | Title | Request Date | Due Date | Follow-up Date | Status | Preparer/s | Notes
1 | 5737 | Panel IDs | 02/16/2021 | 03/02/2021 |  | Closed | Deepak Mugundu Balan | 
2 | 5738 | File and Libraries | 02/16/2021 | 03/09/2021 |  | Closed | Diana L Johnston | 
3 | 6782 | Manual Claims Libraries – Access Permission | 03/17/2021 | 03/26/2021 |  | Certified | Jason Sheedy | 
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”

## Slide 6: Initial Findings
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”
Findings |  |  |  | 
# | Control Area | Findings | Impact | Owner
 | N/A |  |  | 
Notes: Fidelis:

## Slide 7: Initial Observations
Observations |  |  | 
# | Control Area | Observation | Owner
1 | N/A |  | 
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”
Notes: Fidelis:

## Slide 8: Remaining Project Schedule
Project Schedule |  |  | 
Step | Description | Expected Date | Status
1 | Phase I – Planning and Scoping | 01/31/2021 | Complete
2 | Phase II – Control Analysis Walkthrough Interviews & Control Validation | 02/28/2021 | In Progress
3 | Phase III – Fieldwork and Testing Data Analysis & Test Execution | 04/30/2021 | In Progress
4 | Phase IV – Reporting | 05/21/2021 | Not Started
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”

## Slide 9
Appendix
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”