## Slide 1: Benefits Production Access Review Kick-off Meeting
    January 29, 2021

## Slide 2
Engagement Details
Key Milestones
Key Contacts
Expectations
Next Steps
Appendix
  Standard Terminology
  Escalation Protocol
  Prepared at the Request of Legal Counsel: Privileged & Confidential Communication

## Slide 3: Attorney Client Privilege (ACP) Protocol
Legal requests Internal Audit conduct certain reviews to facilitate the Legal Department’s (or outside counsel’s) representation of CVS Health and its subsidiaries in connection with a pending or anticipated litigation or other circumstances. These projects are protected by the Attorney Client Privilege (ACP).
Helps the Company’s Legal counsel understand technical controls/issues in the relevant areas. Portions of the audit process, including reporting, are enhanced to ensure the project is appropriately protected by ACP and/or work product:
  Designated in-house attorney reviews the Kick-Off deck prior to distribution and is invited to the Kick-Off meeting and other applicable status meetings
  The Legend (“Prepared at the Request of Legal Counsel: Privileged & Confidential Communication”) or other ACP disclosure is added to all deliverables, meeting invites and other communications
  Designated in-house attorney is copied on all communications relating to conclusions, findings and action plans
  Deliverables, including the Kick-Off deck and Audit Report, should not be forwarded to any colleagues outside of the distribution list and if responding to the distribution of the Kick-Off deck or Audit Report, the designated attorney should be copied
  Audit Reports and Memos are addressed to the designated in-house attorney

## Slide 4: Engagement Details Executive Summary
The quality assurance (QA) and testing procedures performed once PBM client benefits requirements are setup within the adjudication system provides assurance that setup is complete and accurate, and claims will adjudicate appropriately. As a part of testing and QA, benefits testers submit a series of claim scenarios within the TEST environment to ensure complete and accurate adjudication. Benefits testers should not be granted access to the PROD environment.
In January 2021, 32 Aetna test claims (27 Medicaid and 5 Commercial) were identified as being inadvertently pushed to PROD by benefits testers. After further investigation, it was determined that two benefits testers had inappropriate PROD access and submitted test claims into the PROD environment via the EzTest tool. Impact analyses determined no client or member impact and the claims were appropriately reversed.
David Hummel, VP Client Implementations & Services, and Madhu Kolachina, VP Benefits Operations, have requested Internal Audit perform an access review of Client Benefits Testers to validate no other users have inappropriate PROD access. In addition, management has asked IA to review the Benefits testing and quality assurance processes for opportunities to enhance review procedures to ensure inappropriate submission of test claims to the PROD environment does not occur in the future.
  Prepared at the Request of Legal Counsel: Privileged & Confidential Communication

## Slide 5: Engagement Details Objectives & Inherent Risks
Objective Area | Related Inherent Risk* | Key Areas of Focus
Production Access | Client Benefits Testers inappropriately submit test claims to the production environment, which may result in negative member, client or pharmacy impact. | Validate segregation of duties controls are in place which restrict unauthorized access to enter manual claims in the production environment.
 |  | Review production claim transactions to determine if submitted by appropriate personnel based on job responsibilities.
 | Access to critical RxClaim program files and directories are not restricted or monitored based on individual job responsibilities. | Ensure access to RxClaim program files and directories called on to support the submission of manual claims transactions is restricted based on job responsibilities.
Quality Assurance | QA processes are not designed to identify inappropriate submission of test claims to the production environment, which may result in negative member, client or pharmacy impact. | Review testing and QA processes for opportunities to enhance review procedures to prevent inappropriate submission of test claims to the PROD environment.
Policies and Procedures | Policies and procedures are not documented and/or consistently followed, which may result in improper submission of test claims. | Validate policies and procedures related to Benefits personnel access to TEST and PROD environments are completely and accurately documented and consistently followed.
*Reflects the level of risk that exists in the absence of controls
  Prepared at the Request of Legal Counsel: Privileged & Confidential Communication

## Slide 6: Engagement Details Business Input
Input required from the Business
Recent changes in process or organization
  Various sub-processes or multiple locations
  Any internal/external reviews (e.g. consulting, external audit, process reengineering)
Limitations in resources or process
Existing issues
Other concerns
  Prepared at the Request of Legal Counsel: Privileged & Confidential Communication

## Slide 7: Key Milestones
Audit Milestone | Estimated Completion Date
Planning & Scoping Phase Hold planning and scoping meetings with the Business Area(s) Finalize the scope and objectives of the audit Draft Kick-Off Deck and hold kick-off meeting (if applicable) to discuss audit project and scope | January 2021
Control Analysis Phase Conduct walkthrough meetings Document process understanding Document risks and controls Obtain management alignment with our understanding of the process and controls Design audit test plan | February 2021
Fieldwork & Testing Phase Execute audit test plan Keep management aware of findings as they are identified Validate testing executions with IA management | March 2021
Reporting Phase Obtain management alignment with audit issues Obtain management action plans to address audit issues Draft audit report based on testing findings Hold close meeting (if applicable) to discuss draft audit report with management Obtain alignment with final report before distribution | April 2021
  Prepared at the Request of Legal Counsel: Privileged & Confidential Communication

## Slide 8: Key Contacts Internal Audit & Business Area (Operations)
Internal Audit Team |  | 
Role | Name | Responsibilities
Audit Director(s) | David Horst | Oversight/guidance and liaison with Business Owners
Audit Manager | Heather Boyce | Oversight/guidance and liaison with Business Owners
Lead Auditor | Amber Nadeem Kothawala | Liaison with Business Owners, develop project plan and lead team
Staff Auditors | Resheena Scalero | Liaison with Business Owners, controls analysis and test execution
Business Line Contacts |  | 
Role | Name | Responsibilities
Primary POC Executive Management | David Hummel Madhu Kolachina | Primary Business Owner (VP Level or above)
Primary POC | Sanjay Chablani Len Fusaro Thomas Koester Anne Mall Jason Park Derek Purvis | Transfer knowledge of key business functions, process documentation and key control evidence to the Internal Audit team; control validation and issue ownership.
Key Business Line Contacts listed are a starting point for discussion and not meant to indicate these individuals are responsible for the process, observations and/or report.
Legal Contacts |  | 
Role | Name | Responsibilities
Legal Representative | Matthew Oesterle | Report Owner; Designated in-house attorney for projects performed under Attorney Client Privilege
  Prepared at the Request of Legal Counsel: Privileged & Confidential Communication

## Slide 9: Key Contacts Internal Audit & Business Area (IT)
Internal Audit Team |  | 
Role | Name | Responsibilities
Audit Director(s) | Lynn Atkin Ron Roy | Oversight/guidance and liaison with Business Owners
Audit Manager | Sarah Kubiak | Oversight/guidance and liaison with Business Owners
Lead Auditor | Eric Mata | Liaison with Business Owners, develop project plan and lead team
Staff Auditors | Seun Mafi | Liaison with Business Owners, controls analysis and test execution
Business Line Contacts |  | 
Role | Name | Responsibilities
Primary POC Executive Management | Ajoy Kodali Bobby Mukundan Srithal Bellary Heather LaPolt | Primary Business Owner (VP Level or above)
Primary POC | Ken Park Pranav Gupta Deepak Mugundu Balan Mitchell Super Greg Bradley Markus Watson Jeff Steele | Transfer knowledge of key business functions, process documentation and key control evidence to the Internal Audit team; control validation and issue ownership.
Key Business Line Contacts listed are a starting point for discussion and not meant to indicate these individuals are responsible for the process, observations and/or report.
  Prepared at the Request of Legal Counsel: Privileged & Confidential Communication

## Slide 10: Expectations Internal Audit & Business Line
What Internal Audit expects from your Team:
Awareness and engagement
All relevant documentation, including process/control documentation, policies & procedures, key reporting and dependencies be provided promptly during the planning phase
Management and staff will make reasonable time available for interviews, provide prompt responses to follow-up questions and deliver requested support or information by agreed upon due dates
All layers of management in your Team’s organization are kept informed of identified exceptions and issues
Management will review the Draft Audit Report in advance of the close meeting to allow for a more targeted discussion
What you can expect from Internal Audit:
Prompt notification of concerns, such as audit issues or roadblocks
Potential unfamiliarity with business process
Focus on key areas of high risk
Ongoing communication throughout the project
Draft Audit Report will be provided for the business’ review at least 24 hours in advance of the close meeting
  Prepared at the Request of Legal Counsel: Privileged & Confidential Communication

## Slide 11: Additional Information to Consider
AuditBoard is the audit management tool used by Internal Audit
  Internal Audit may leverage this system for the following aspects of the project:
    Centrally manage and communicate requests
    Gain alignment with verbiage of Findings and Observations
      Request Management’s Remediation Plan for inclusion within the Audit Report
    Management of Findings upon the conclusion of the audit
    Note: Please do not upload any PII / PHI to AuditBoard; please discuss with Internal Audit the most appropriate means to transmit any sensitive documentation requested as part of this project
Audit Surveys will be sent at the conclusion of the audit to the relevant business contacts
  Audit Surveys help Internal Audit aggregate feedback on what went well during the project and areas of opportunity for the team to reflect on going forward
    Survey will be deployed from AuditBoard typically within 1-2 weeks of report issuance
    Results are gathered centrally by our Department administrative team and feedback is anonymously provided back to the respective Internal Audit team
  Prepared at the Request of Legal Counsel: Privileged & Confidential Communication

## Slide 12: Next Steps
Alignment with project scope from the business
Issuance of Kick-Off deck to formalize kick-off of the project
Schedule walkthrough meetings with relevant business contacts
Schedule periodic status meetings with the business to keep open line of communication
  Prepared at the Request of Legal Counsel: Privileged & Confidential Communication

## Slide 13: Appendix

## Slide 14: Standard Terminology Overall Control Environment Opinion
Effective | Overall, controls are appropriately designed and functioning as intended. Control weaknesses, if noted, do not threaten the effectiveness of the process reviewed.
Mostly Effective | Except for the issues noted, controls in place provide reasonable assurance that business risks are adequately mitigated.
Improvement Needed | One or more significant control weaknesses exist that require prompt action to prevent the process from becoming ineffective.
Ineffective | Control weaknesses are pervasive or one weakness is so severe that it impacts the entire operation under review. Immediate management attention is needed to remediate the issue identified.
  Prepared at the Request of Legal Counsel: Privileged & Confidential Communication

## Slide 15: Standard Terminology Ratings & Management Action Plan
High | The identified risk requires the immediate attention of department and senior management to prevent the process from becoming ineffective, and an agreed-upon action plan for resolution is needed.
Medium | The identified risk requires the near-term attention of the responsible manager. There should be an agreed-upon action plan for its resolution.
Low | The identified risk does not warrant immediate attention; however, there should be an agreed-upon action plan for ultimate resolution.
Deficiency | If SOX related, rating categories will be assessed as Deficiency, Significant Deficiency, or Material Weakness. Note: While the audit will focus on the objectives previously noted, IA has a responsibility to assess any additional risks identified during the audit, and report any issues identified. Where applicable, issues will also be evaluated against requirements for Sarbanes-Oxley or other regulatory standards.
The rating of findings drives the timing of remediation and also the level of management that is responsible for developing and implementing action plans.
Each Management Action Plan requires a remediation due date which is tracked by IA.
Remediation Due Date | Reflects the time required for Management to complete the agreed upon action plan, as well as time for IA to complete the associated validation procedures to ensure the action plan has been implemented effectively.
  Prepared at the Request of Legal Counsel: Privileged & Confidential Communication

## Slide 16: Escalation Protocol
Potential Causes for Escalation
Data requests not received within expected timeframes
Data provided does not align with follow-up requests for clarification
Key attendees miss walkthrough meetings following confirmed schedules
Internal Audit is denied access to key data or people that may impact findings
Management accepts a level of residual risk not acceptable to the organization
Management is not aligned with identified issues, risk priority ratings and/or the overall audit opinion
Escalation Process – when one or more of the above events occur
Convey the issue to the next level of management
The responsible SVP / VP may be notified of causes which delay audit execution
Escalations may be tracked and reported during recurring status meetings with management
The CAE may discuss with Senior Management and the Audit Committee, if necessary
  Prepared at the Request of Legal Counsel: Privileged & Confidential Communication

## Slide 18: Distribution List
Business Area | Internal Audit
Sanjay Chablani Len Fusaro David Hummel Thomas Koester Madhu Kolachina Anne Mall Jason Park Derek Purvis | Lynn Atkin Heather Boyce David Horst Sarah Kubiak Seun Mafi Eric Mata Amber Nadeem Ronald Roy Resheena Scalero
PBM IT Systems | Enterprise Technology Services
Deepak Mugundu Balan Srithal Bellary Greg Bradley Pranav Gupta Ajoy Kodali Ken Park Jeff Steele Markus Watson | Bobby Mukundan Heather LaPolt Mitchell Super
Legal | Compliance
Matthew Oesterle Anna Shimanek | Myatt Meier Tom Pawlik
  Prepared at the Request of Legal Counsel: Privileged & Confidential Communication