## Slide 1
20335 – Benefits Production Access
Status Report:
04/07/2021

## Slide 2: AGENDA
Project Status | 
Walkthroughs & Meetings | 
Data Requests | 
Initial Observations | 
Appendix | 
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”

## Slide 3: Project Status
As of 04/6/2021
Planning and Scoping Phase – Complete ​Kick-Off deck distributed to stakeholders on 3/19/2021. Control Analysis Phase – In Progress 3 controls in process of validation with owners. Fieldwork Phase – In Progress Evidence has been received and is currently being analyzed. Reporting Phase – Not Started
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”

## Slide 4: Walkthroughs & Meetings
 |  | Meeting Schedules |  |  |  |  | 
 | Team | Meeting Topic | Scheduled Date | Completed Date | Follow up Date | Completed Date | Attendees
1 | (IT) | Benefits Production Access Review – Background (Green Screen Demo) | 02/05/2021 | 02/05/2021 |  |  | Angela Dickinson, Martin Mangin
2 | (IT) | Manual Claims – Access Discussion | 02/12/2021 | 02/12/2021 |  |  | Pranav Gupta, Deepak Mugundu, Aizaz Ahmad, Markus Watson, Jeffery Steele, Joshua Godfrey, John Gloster, Sheila Barbour
4 | (IT) | EzTest Tool Walkthrough | 03/18/2021 | 03/18/2021 |  |  | Hemanth Pappu, Mohan Manchashetty, Aizaz Ahmad, Ganga Merneedi
5 | (Ops) | HP - Quality Assurance and Release Management Process walkthrough | 03/08/2021 | 03/08/2021 |  |  | Narsimha Namburi, Robyn Martin, Amber Nadeem Kothawala, Rajendra Jupaka, Sandanalakshmy Pajany Nayadu
6 | (Ops) | Employer Commercial - Quality Assurance and Release Management Process Walkthrough | 03/09/2021 | 03/09/2021 |  |  | Shalin Nath, Matthew Benger, Heather Boyce, Robyn Martin, Amber Nadeem Kothawala
7 | (Ops) | Aetna - Quality Assurance and Release Management Process Walkthrough | 03/11/2021 | 03/11/2021 |  |  | Jason Park, Faisal Naeem, Heather Boyce, Robyn Martin, Amber Nadeem Kothawala
8 | (IT) | Manual claim libraries - User groups and Permissions | 3/31/2021 | 03/31/2021 |  |  | Mitchell Super, Aizaz Ahmad, Diana Johnston, Nicole Frazier, Kathie Graceffa
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”

## Slide 5: Walkthroughs & Meetings Cont’d
 |  | Meeting Schedules |  |  |  |  | 
 | Team | Meeting Topic | Scheduled Date | Completed Date | Follow up Date | Completed Date | Attendees
1 | (IT) | Panel ID Access - Walkthrough | 04/01/2021 | 04/01/2021 |  |  | Diana Johnston, Aizaz Ahmad
2 | (IT) | Manual Claims – Access Discussion (II) | 04/06/2021 | 04/06/2021 |  |  | Pranav Gupta, Deepak Mugundu, Aizaz Ahmad
4 |  |  |  |  |  |  | 
5 |  |  |  |  |  |  | 
6 |  |  |  |  |  |  | 
7 |  |  |  |  |  |  | 
8 |  |  |  |  |  |  | 
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”

## Slide 6: Open Data Requests – as of 04/06/2021
 |  | Data Requests |  |  |  |  |  |  | 
# | Team | UID | Title | Request Date | Due Date | Follow-up Date | Status | Preparer/s | Additional Preparer/s
1 | (IT) | 5737 | RxClaim – Manual claim Panel IDs | 02/16/2021 | 03/02/2021 |  | Closed | Deepak Mugundu Balan | Pranav Gupta
2 | (IT) | 5738 | Files and Libraries | 02/16/2021 | 03/09/2021 |  | Closed | Diana L Johnston | Pranav Gupta, Deepak Mugundu Balan, Michael ONeill
3 | (IT) | 6782 | Manual Claims Libraries – Access Permission | 03/17/2021 | 03/26/2021 |  | Closed | Jason Sheedy | Mitchell Super, Conway Norwood II, Deepak Mugundu Balan
4 | (Ops) | N/A | Active Benefit Testers Listing | 1/27/2021 | 02/01/2021 |  | Closed | Faisal Naeem | 
 |  |  |  | 1/27/2021 | 02/16/2021 |  | Closed | Narsimha Namburi | 
 |  |  |  | 1/27/2021 | 02/04/2021 |  | Closed | Dinakar Anumolu | 
 |  |  |  | 1/27/2021 | 03/02/2021 |  | Closed | Kimberly Archibald | 
 |  |  |  | 1/27/2021 | 02/04/2021 |  | Closed | Kishore Korapati | 
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”

## Slide 7: Open Data Requests Cont’d – as of 04/06/2021
 |  | Data Requests |  |  |  |  |  |  | 
# | Team | UID | Title | Request Date | Due Date | Follow-up Date | Status | Preparer/s | Additional Preparer/s
5 | (Ops) | N/A | SalesForce.com screenshots and attachments for Aetna claims | 03/26/2021 | 04/02/2021 |  | Closed | Holly Burrington | 
6 | (IT) | 7122 | Manual Claims Libraries- Access Permissions (II) | 04/01/2021 | 04/02/2021 |  | Certified | Mitchell Super | 
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”

## Slide 8: Initial Findings
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”
Findings |  |  |  | 
# | Control Area | Findings | Impact | Owner
1 | Manual Claims Submission | IA obtained listings of all active Benefits Testers and compared to a listing of all users with PREPROD and PROD access to the Manual Green Screens. From this analysis, IA identified 191 Benefit Testers, including both onshore and offshore users, with inappropriate “read and update” access to the PROD environment. Per review of the rationales IA obtained from applicable leaders, it was noted that Benefit Testers need read-only access to PROD Manual Green Screens to perform claims testing. Additionally, it was brought to IA’s attention, that issues arise when attempting to revoke PROD access for onshore members because PROD access cannot be removed without removing the PREPROD access users require to perform testing. | TBD | TBD
Notes: Fidelis:

## Slide 9: Initial Observations
Observations |  |  | 
# | Control Area | Observation | Owner
1 |  |  | 
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”
Notes: Fidelis:

## Slide 10: Remaining Project Schedule
Project Schedule |  |  | 
Step | Description | Expected Date | Status
1 | Phase I – Planning and Scoping | 01/31/2021 | Complete
2 | Phase II – Control Analysis Walkthrough Interviews & Control Validation | 02/28/2021 | In Progress
3 | Phase III – Fieldwork and Testing Data Analysis & Test Execution | 04/30/2021 | In Progress
4 | Phase IV – Reporting | 05/31/2021 | Not Started
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”

## Slide 11
Appendix
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”

## Slide 12: Standard Terminology Ratings & Management Action Plan
High | The identified risk requires the immediate attention of department and senior management to prevent the process from becoming ineffective, and an agreed-upon action plan for resolution is needed.
Medium | The identified risk requires the near-term attention of the responsible manager. There should be an agreed-upon action plan for its resolution.
Low | The identified risk does not warrant immediate attention; however, there should be an agreed-upon action plan for ultimate resolution.
Deficiency | If SOX related, rating categories will be assessed as Deficiency, Significant Deficiency, or Material Weakness. Note: While the audit will focus on the objectives previously noted, IA has a responsibility to assess any additional risks identified during the audit, and report any issues identified. Where applicable, issues will also be evaluated against requirements for Sarbanes-Oxley or other regulatory standards.
The rating of findings drives the timing of remediation and also the level of management that is responsible for developing and implementing action plans.
Each Management Action Plan requires a remediation due date which is tracked by IA.
Remediation Due Date | Reflects the time required for Management to complete the agreed upon action plan, as well as time for IA to complete the associated validation procedures to ensure the action plan has been implemented effectively.
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”
12

## Slide 13: Escalation Protocol
Potential Causes for Escalation
Data requests not received within expected timeframes
Data provided does not align with follow-up requests for clarification
Key attendees miss walkthrough meetings following confirmed schedules
Internal Audit is denied access to key data or people that may impact findings
Management accepts a level of residual risk not acceptable to the organization
Management is not aligned with identified issues, risk priority ratings and/or the overall audit opinion
Escalation Process – when one or more of the above events occur
Convey the issue to the next level of management
The responsible SVP / VP may be notified of causes which delay audit execution
Escalations may be tracked and reported during recurring status meetings with management
The CAE may discuss with Senior Management and the Audit Committee, if necessary
“Privileged & Confidential; Prepared at the request of Legal; Attorney Work Product.”
13