## RACI Matrix (IT Audit)
Project Deliverable (or Activity) |  | Sr. Director | Director | Manager | Advisor/APM | Sr. Consultant | Sr. Consultant | Consultant | Sr. Consultant | Consultant
|  | Oversight |  |  | Lead |  | Sub-Lead |  | Staff
Planning Phase | A.1 - Planning and Scoping Notification | I | I | A | R | R |  |  |  |  | IT IA RACI Matrix Legend
| A.2.1 - Background Review |  | C | A | R | R | C | C |  |  | Acronym | Title | Description
| A.2.2 - Risk Stakeholder Input | I | I | A/R | C | C | C |  |  |  | R | Responsible | Those who do the work to complete the task. There is at least one role with a participation type of responsible, although others can be delegated to assist in the work required.
| A.2.3 - Planning and Scoping Meetings |  | I | A | R | R | C
| A.2.4 - Fraud Risk Assessment |  |  | A | R | R | C | C | C | C | A | Accountable | The one ultimately answerable for the correct and thorough completion of the deliberable or task, the one who ensures the prerequisites of the task are met and who delegates the work to those responsible. The accountable must sign off (approve) work that responsible provides. There must be one accountable specificed for each task or deliverable.
| A.2.5 - Scope Document |  |  | A | R | R | C
| A.2.6 - Drafting the Scope and Objectives | I | I/C | A | R | R
| A.3.1 - Scoping and Planning Data Analytics |  |  | A | R | R | C | C | C | C
| A.4 - Audit Work Breakdown |  | I | A | R | R |  |  |  |  | C | Consulted | Those whose opinions are sought, typically subject matter experts; and with whom there is two-way communication
| A.5.1 - Kick-Off Deck |  | I/C | A | A | R | R |  | C
| A.5.2 - Kick-Off Meeting | I | I | A | R | R | R |  |  |  | I | Informed | Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication.
| A.6.1 - Business Status Updates |  | I | I | A | R | R
| A.6.2 - Internal Status Updates |  | I | I | A | R | R | C | R/C | C
Control Analysis Phase | B.1 - Walkthroughs |  |  | I | A | R | R | R | R | R
B.2.1 Narratives | bar: I to C
B.2.2 - Process Flows | bar: I to C
| B.3.1 - Drafting the RCA |  | I | A | R | R | R/I | I | I | I
| B.3.2 - Internal RCA review |  | I: A; A: R; R: C; R: C
| B.3.3 - Business Area Validation of RCA or Process Flow |  | I | A | R | R | R
Testing and Fieldwork Phase | C.1 - Leadsheets |  |  | I | A | R | R | R | R | R
| C.2.1 - Sample Sizes |  |  | I | A | R | R | R | R | R
| C.2.2 - Additional Sample for Errors Identified |  |  | I | A | A | R | R | R | R
| C.3.1 Request Procedures for Supporting Documentation |  |  | I | A | A | R | R | R | R
| C.3.2 Workpapers |  |  | I | A | A | R | R | R | R
C.3.3 - Naming Conventions | bar: R to I
| C.4 - Audit Review |  | I | A | R | R | R/C/I | I | I | I
Reporting Phase | D.1.1 - Audit Summary Page |  | C | A | R | R | C | C
| D.1.2 - Findings & Management Action Plans | I | C | A | R | R | R | C | C | C
| D.1.3 - Observations | I | C | A | R | R | R | C | C | C
D.1.4 - Standard Terminology | bar: A A to R R
D.1.5 - Distribution List | bar: I I to R R
| D.2.1 - Closing Meeting | I | I | A | R | R | R | I | I | I
| D.2.2 - Final Review | I I: I; C C: A; A A: R; R R: R/C; R R: R/C
Post-Issuance Phase | E.1.1 - Completion Status | I I: I; C C: I; A A: A; R R: R; R R: R
| E.2 - Audit Close Checklist |  | I | A | I | I | R | R | R | R
| E.3 - Closing Projects | I I: I; C C: I; A A: A; R R: R; R R: R
E.4 - Audit Survey | bar: I I to C C
E.5 - Audit Staff Evaluations | bar: A A to R R
| E.6.1 - On-going Communication |  | I | I | A | A | R | R | I | I
| E.6.2 - Due Date Extensions | C | C | A | R | R | I | I | I | I
| E.6.3 - Finding Validation Procedures |  | I | I | A | A | R | R | R | R
| E.6.4 - Failed Validation Procedures | I | C | C | A | A | R | R | R | R
| E.6.5 - Closing an Audit Finding | I | I | A | A | R | R | R | R | R

## RACI Matrix - Role Based
Project Deliverable (or Activity) |  | Sr. Director | Director | Manager | Advisor/APM | Sr. Analyst | Sr. Analyst | Analyst | Sr. Analyst | Analyst
|  | Oversight |  |  | Lead |  | Sub-Lead |  | Staff
Planning Phase | A.1 - Planning and Scoping Notification | I/A |  |  | R | [5 empty] | IT IA RACI Matrix Legend
| A.2.1 - Background Review | C/A |  |  | R |  | C |  |  |  | Acronym | Title | Description
| A.2.2 - Risk Stakeholder Input | I/A/R |  |  | C |  | C |  |  |  | R | Responsible | Those who do the work to complete the task. There is at least one role with a participation type of responsible, although others can be delegated to assist in the work required.
| A.2.3 - Planning and Scoping Meetings | I/A |  |  | R |  | C
| A.2.4 - Fraud Risk Assessment | A |  |  | R |  | C |  | C |  | A | Accountable | The one ultimately answerable for the correct and thorough completion of the deliberable or task, the one who ensures the prerequisites of the task are met and who delegates the work to those responsible. The accountable must sign off (approve) work that responsible provides. There must be one accountable specificed for each task or deliverable.
| A.2.5 - Scope Document | A |  |  | R |  | C
| A.2.6 - Drafting the Scope and Objectives | I/C/A |  |  | R
| A.3.1 - Scoping and Planning Data Analytics | A |  |  | R |  | C |  | C
| A.4 - Audit Work Breakdown | I/A |  |  | R | [5 empty] | C | Consulted | Those whose opinions are sought, typically subject matter experts; and with whom there is two-way communication
| A.5.1 - Kick-Off Deck | I/C/A |  |  | A/R |  | R |  | C
| A.5.2 - Kick-Off Meeting | I/A |  |  | R |  | R |  |  |  | I | Informed | Those who are kept up-to-date on progress, often only on completion of the task or deliverable; and with whom there is just one-way communication.
| A.6.1 - Business Status Updates | I |  |  | A/R |  | R
| A.6.2 - Internal Status Updates | I |  |  | A/R |  | R/C |  | R/C
Control Analysis Phase | B.1 - Walkthroughs | I |  |  | A/R |  | R |  | R
| B.2.1 Narratives | A |  |  | A/R |  | R |  | R
| B.2.2 - Process Flows | A |  |  | A/R |  | R |  | R
| B.3.1 - Drafting the RCA | I/A |  |  | R |  | R/I |  | I
| B.3.2 - Internal RCA review | A/R |  |  | C
| B.3.3 - Business Area Validation of RCA or Process Flow | I/A |  |  | R |  | R
Testing and Fieldwork Phase | C.1 - Leadsheets | I |  |  | A/R |  | R |  | R
| C.2.1 - Sample Sizes | I |  |  | A/R |  | R |  | R
| C.2.2 - Additional Sample for Errors Identified | I |  |  | A |  | R |  | R
| C.3.1 Request Procedures for Supporting Documentation | I |  |  | A |  | R |  | R
| C.3.2 Workpapers | I |  |  | A |  | R |  | R
| C.3.3 - Naming Conventions |  |  |  | A |  | R |  | R
| C.4 - Audit Review | I/A |  |  | R |  | R/C/I |  | I
Reporting Phase | D.1.1 - Audit Summary Page | C/A |  |  | R |  | C
| D.1.2 - Findings & Management Action Plans | I/C/A |  |  | R |  | R/C |  | C
| D.1.3 - Observations | I/C/A |  |  | R |  | R/C |  | C
| D.1.4 - Standard Terminology | I |  |  | R |  | R
| D.1.5 - Distribution List | A/R |  |  | R |  | R
| D.2.1 - Closing Meeting | I/A |  |  | R |  | R/I |  | I
| D.2.2 - Final Review | I/A/R |  |  | R/C
Post-Issuance Phase | E.1.1 - Completion Status | I/A |  |  | R
| E.2 - Audit Close Checklist | I/A |  |  | I |  | R |  | R
| E.3 - Closing Projects | I/A |  |  | R
| E.4 - Audit Survey | I/A |  |  | I |  | I |  | I
| E.5 - Audit Staff Evaluations | A |  |  | R
| E.6.1 - On-going Communication | I |  |  | A |  | R |  | I
| E.6.2 - Due Date Extensions | C/A |  |  | R |  | I |  | I
| E.6.3 - Finding Validation Procedures | I |  |  | A |  | R |  | R
| E.6.4 - Failed Validation Procedures | I/C |  |  | A |  | R |  | R
| E.6.5 - Closing an Audit Finding | I/A |  |  | A/R |  | R |  | R