## Slide 1: 21115 – Enterprise Person Hub (EPH) Status Update
11/18/2021

## Slide 2: AGENDA
Project Status | 
Walkthroughs & Meetings | 
Data Requests | 
Initial Discoveries | 
Appendix | 
©2021 CVS Health and/or one of its affiliates: Confidential & Proprietary

## Slide 3: Audit Progress – Current Status
The audit is currently in the Testing Phase.
Audit is expected to be completed on time.  There are no discoveries identified at this time.
Milestones | Timing* | Status | Comments
Planning Phase |  |  | 
Perform Initial Walkthroughs | November 2021 | Complete | 
Validate Risk Control Analysis | November 2021 | In Progress | Follow up questions on RCA Validation sent out to Wijendran on 11/17/2021
Testing Phase |  |  | 
Testing Execution | December 2021 | In Progress | 11 out of 11 tests in progress.
Reporting Phase |  |  | 
Validation of Discoveries (if applicable) | January 2022 | On Track | 
Management Action Plan (MAP) (if applicable) | January 2022 | On Track | 
Distribute Audit Report | January 2022 | On Track | 
*Completion date

## Slide 4: Walkthroughs & Meetings
 | Meeting Schedules |  |  |  |  |  | 
 | Meeting Topic | Attendees | Scheduled Date | Status | Follow up Required | Follow up Date | Notes
1 | CVS ID Walkthrough | Seun Mafi, Nazare Jason, Vazquez Sol, Monika Godera, Tyrell Jarett, Terri Ann G Quiambao, Joseph Rocha, Wijendran Nadesan, N Nijesh, Ron Ronald J, Carmen Malangone, David Dessommes | 10/25/2021 | Complete | No | N/A | 
2 | Data Integrity Walkthrough | Seun Mafi, Jason Nazare, Monika Godera, Roy Ronald J, Carmen Malangone, David Dessommes, Nadesan Wijendran, N Nijesh, Sol Vazquez, Tyrell Jarrett, Joseph Rocha, Terri Ann G Quiambao, Sourabh Mayya | 10/28/2021 | Complete | No | N/A | 
3 | Access Management Walkthrough | Seun Mafi, Monika Godera, Ronald J Roy, Carmen Malangone, David Dessommes, Nadesan Wijendran, N Nijesh, Sol Vazquez, Jason Nazare, Tyrell M Jarrett, Joseph Rocha, Terri Ann G Quiambao | 11/1/2021 | Complete | No | N/A | 

## Slide 5: Walkthroughs & Meetings
 | Meeting Schedules |  |  |  |  |  | 
 | Meeting Topic | Attendees | Scheduled Date | Status | Follow up Required | Follow up Date | Notes
4 | Data Protection Walkthrough | Seun Mafi, Monika Godera, Nadesan Wijendran, N Nijesh, Sol Vazquez, Jason Nazare, Tyrell Jarett, Joseph Rocha, Terri Ann G Quiambao, Ronald J Roy, Carmen Malangone, David Dessommes | 11/2/2021 | Complete | Yes | 11/8/2021 | 
5 | Scalability and Availability Walkthrough | Seun Mafi, Monika Godera, Wijendran Nadesan, N Nijesh, Sol Vazquez, Jason Nazare, Tyrell M Jarett, Joseph Rocha, Terri Ann G Quiambao, Ronald J Roy, Carmen Malangone, David Dessommes | 11/5/2021 | Complete | No | N/A | 
6 | Follow up (Data Protection) Walkthrough | Monika Godera, Nadesan Wijendran, N Nijesh, Sol Vazquez, Seun Mafi, Tyrell Jarett, Joseph Rocha, Terri Ann G Quiambao, Ronald J Roy, Carmen Malangone, David Dessommes | 11/8/2021 | Complete | No | N/A | 
7 | Duplicate Management Walkthrough | Tyrell Jarrett, Sol Vazquez, Monika Godera, Seun Mafi, David Dessommes, Nadesan Wijendran Carmen Malangone | 11/18/2021 | Not Started | N/A | N/A | 

## Slide 6: Open Requests – as of 9:00 AM ET on 11/18
 | Data Requests |  |  |  |  |  |  | 
# | UID | Title | Request Date | Due Date | Status | Preparers | Subscribers | Notes
1 | 12884 | A.1 - CVS ID Creation Management | 11/17/2021 | 11/19/2021 | Submitted | Nadesan Wijendran | David Dessommes, Ronald Roy, Monika Godara, Joseph Rocha, Seun Mafi, Terri Ann Quiambao, Sol Vazquez | 
2 | 12886 | C.1 - User Access Provisioning | 11/17/2021 | 11/19/2021 | Closed | Nadesan Wijendran | David Dessommes, Ronald Roy, Monika Godara, Joseph Rocha, Seun Mafi, Terri Ann Quiambao, Sol Vazquez | 
3 | 12892 | E.1 – System Performance: Alert Thresholds/Configurations | 11/17/2021 | 11/19/2021 | Open | Nadesan Wijendran | David Dessommes, Ronald Roy, Monika Godara, Joseph Rocha, Seun Mafi, Terri Ann Quiambao, Sol Vazquez, Tyrell Jarrett | 
4 | 12893 | E.2 Event Monitoring: Quarterly and Monthly Reports | 11/17/2021 | 11/19/2021 | Open | Nadesan Wijendran | David Dessommes, Ronald Roy, Monika Godara, Joseph Rocha, Seun Mafi, Terri Ann Quiambao, Sol Vazquez, Tyrell Jarrett | 
5 | 12897 | B.1 – Completeness Validation Checks | 11/17/2021 | 11/192021 | Inactive | Nadesan Wijendran | David Dessommes, Ronald Roy, Monika Godara, Joseph Rocha, Seun Mafi, Terri Ann Quiambao, Sol Vazquez, Tyrell Jarrett | 
6 | 12898 | B.2 – Accuracy Validation Checks | 11/17/2021 | 11/19/2021 | Inactive | Nadesan Wijendran | David Dessommes, Ronald Roy, Monika Godara, Joseph Rocha, Seun Mafi, Terri Ann Quiambao, Sol Vazquez, Tyrell Jarrett | 

## Slide 7: Discoveries Identified The following discoveries were identified and will be discussed with applicable business owners to ensure alignment. These are considered draft and subject to change until the final report is issued.
No. | Initial Discoveries
1 | 

## Slide 8: Appendix

## Slide 9: Key Milestones
Audit Milestone | Estimated Completion Date
Planning & Scoping Phase Hold planning and scoping meetings with the Business Area(s) Finalize the scope and objectives of the audit Draft Kick-Off Deck and hold kick-off meeting (if applicable) to discuss audit project and scope | October 2021
Control Analysis Phase Conduct walkthrough meetings Document process understanding Document risks and controls Obtain management alignment with our understanding of the process and controls Design audit test plan | November 2021
Fieldwork & Testing Phase Execute audit test plan Keep management aware of findings as they are identified Validate testing executions with IA management | December 2021
Reporting Phase Obtain management alignment with audit issues Obtain management action plans to address audit issues Draft audit report based on testing findings Hold close meeting (if applicable) to discuss draft audit report with management Obtain alignment with final report before distribution | January 2022

## Slide 10: Audit Scope
Audit Scope
To validate that controls are designed effectively to ensure demographic data is governed, secured, complete, and accurately maintained within Enterprise Person Hub.
  Estimated Completion Date: January 2022

## Slide 11: Engagement Details Objectives & Inherent Risks
Objective Area | Related Inherent Risk* | Key Areas of Focus
Controls are in place to ensure ID creation is managed adequately. | CVS IDs may unintentionally be created, updated, or deleted resulting in erroneous data in EPH. | CVS IDs are created, updated/edited, and deleted completely and accurately, and to ensure duplicates do not exist
Data integrity controls are in place to ensure data entering EPH is complete and accurate. | Data integrity and daily balance controls between the source systems and EPH are not in place and the data does not reconcile for completeness and accuracy | Data validation checks are performed between the source systems and EPH Data integrity alerts are communicated and remediated timely per defined SLAs
Access controls are in place to ensure access to the database is appropriately managed by authorized individuals | Access to the database may not be adequately restricted or monitored, resulting in unauthorized access and changes | Access to IBM MDM is restricted adequately Provisioning Recertification Access activities are logged and monitored
*Reflects the level of risk that exists in the absence of controls

## Slide 12: Engagement Details Objectives & Inherent Risks
Objective Area | Related Inherent Risk* | Key Areas of Focus
Data protection controls are in place to ensure data is secured in transit and at rest | Data in transit and at rest is not secure to prevent unauthorized access to confidential, proprietary, or otherwise sensitive data | Ensure data in transit and data at rest is encrypted in accordance with company standards Encryption/masking methods are used for protecting data stored in IBM MDM Encryption methods are in place for data in transit
Scalability and availability controls are in place to support large volumes of data | Technology infrastructure supporting EPH is unable to support large volumes of data | EPH is measured and monitored to ensure the technology infrastructure is scalable to support large volumes data
*Reflects the level of risk that exists in the absence of controls