## Summary (hidden)
Sl No | CR Name | Effort | Comments
1 | Poloris | 5 per week for now. Need to revisit post 03/18 go live.
2 | Coram SFDC | 15 hrs/week
3 | Avail | 15 hrs/week | Approved by Srini on 3/12
4 | Intradiem | 20 hrs/month | Comment from Srini. Onboard this in-lieu of McKesson. Cognizant will start support immediately. Change will reflect in the SOW when the next CR happens
5 | Specialty IVR | 15 hrs / week
6 | EZClaim | Ask : 8 hrs/week | 3/25: Currently in UAT. Moving into Prod in 3 to 4 months.
3:18 : Meeting with T3 rescheduled
Mike to get funding details from Ganga/team.
7 | Tivoli - Specialty |  | 3:18 : Current support team members will support Tivoli jobs for the apps that are in Cognizant scope. Mangesh will close the loop with Mike Reese.

## CR Tracker
Sl No | CR Description | Application name | Tower | Requested by | Req Date | Retirement date | CR category | Cost credit or increase effective date in the SOW | Effort | SoW Scope | CR Status | Approval Status | Comments
1 | Tivoli related activities support | Tivoli - Specialty | Spl | Mike Reese | [7 empty] | N/A | 03/17 : Current support team members will support Tivoli jobs for the apps that are in Cognizant scope. Mangesh will close the loop with Mike Reese. 03/16: Tivoli support work for jobs in Prod, respective support team members to support. New project work will be handled thru Clarity (Mohit) 03/15: Mike agreed to do give capital hours for the Tivoli project work that Mohit is currently doing
2 | New application intake | Poloris | Spl | Ganesh |  |  | New app |  | 32 hours / week (25+7) | Yes | T&M Scope | Approved
3 | New application intake | Coram SFDC | Spl | Ganesh |  |  | New app |  | 15 hours/week | Yes | T&M Scope | Approved
4 | New application intake | Avail | Spl | JZ |  |  | New app |  | 15 hours/week | No | T&M Scope | Approved | 03/12: Approved by Srini for clarity
5 | New application intake | Intradiem | Spl | Mike Reese |  |  | New app |  |  | No | MSM scope - Swap with McKesson Effective date of change: 04/26 | Approved | 04/15: KT will start from 04/19. Steady state 04/26. New charges will be effective 04/26 03/17: Confirmed McKesson was sunset. 03/15: This will have to be taken up in place of an existing application that is retiring
6 | New application intake | Specialty IVR | MMCS | Ganesh |  |  | New app |  | 03/09: 8 hours / week to begin with. | No |  | Approved | 03/22: Support started in T&M mode 03/15: email sent to Ganesh to confirm 15 hrs / week
7 | New application intake | EZClaim | Adj | Mike ONeill |  |  | New app |  | 03/17 : 160 hours (Azure skill set) | No |  |  | 04/29: Decided not to go for non prod support. Will take over the support once the application is moved to production. Will be on hold for now. 04/15: Ganesh / Mike O will talk to Srinivas for the next steps 04/15: Not in production yet, decision to be made for the support
8 | Application retirement | McKesson | Spl | Mike Reese |  | 2021-02-24 | App support decommission |  |  | Yes | MSM scope - Swap with Intradiem Effective date of change: 04/26 | Approved | 04/22: Srinivas agreed that the cost reduction don't have to be done back dated 04/15: Ganesh recommended to remove the charges effective 10/16/20. Hari to get back after validating with Venkat / Kiran.
9 | CSL - Penalty pool % changes | NA | All | Srinivas | 2021-04-29 | [6 empty] | Approved | 05/14: Approved by Ganesh 05/14: Cognizant agreed with the recommended realloation of pool %. Will inlcude in the upcoming CR.
10 | New application intake | Letter admin tool | SPL | Mike Reese | March '21 |  | New app |  | TBD | No |  |  | 05/13: Awaiting input from SME for effort estimation
11 | Application retirement | ACEYUS REPORTING | MMCS | Ganesh | 2021-04-29 | 2021-02-24 | Retirement |  |  | Yes |  |  | 05/13:Cognizant agreed to descope the application
12 | Application retirement | CPR+ GENEVAWOODS | Spl | Ganesh | 2021-04-29 | 2021-09-30 | Retirement | [5 empty] | 05/13:Cognizant agreed to descope the application
13 | Application retirement | FILE TRACKER - BUSINESS MONITOR | Adj | Mike ONeill | 2021-05-10 | 2021-09-30 | Retirement | [5 empty] | 05/13: Part of the functionality is moving to EWF
14 | Application retirement | FILE TRACKER - XML BUILDER | Adj | Mike ONeill | 2021-05-10 | 2021-07-30 | Retirement | [5 empty] | 05/13: Part of the functionality is moving to EWF
15 | Application retirement | MOXIE | MMCS | Ganesh | 2021-04-29 | 2021-03-26 | Retirement | [5 empty] | 05/13:Cognizant agreed to descope the application
16 | New application intake | COLA | Adj | Mike ONeill | 2021-05-10 | Tentative 09/30/2021 | Retirement | [5 empty] | 05/13: Support is still there, analysis in progress
17 | Application enhancement | EWF | Adj | Mike ONeill | 2021-05-10 |  | Existing; Functionality consolidation | [5 empty] | 05/14: Functionality of retired applications getting consolidated in EWF. Pricing band require change, Cognizant is working on the procing band proposal.
18 | Application enhancement | Secure transport | Adj | Mike ONeill | 2021-05-10 |  | Existing; Functionality consolidation
19 | New application intake | Coram VAX | Spl | Mike Reese | 2021-04-26 |  |  |  | 1 FTE |  |  | Rejected by Srini | 06/24: Srinivas rejected the proposal 05/28: To be reviewed with Srinivas on 06/04
20 | New application intake | NLX CTE | Spl | Mike Reese | 2021-04-26 |  |  |  | 2 FTE |  |  | On Hold: Awaiting final decision | 06/24: Srinivas suggested to put this on hold as this require clarification on the funding source. 06/04: Received approval from Mike to proceed with the staffing. Will be supported in T&M mode. 06/04: Mike & Ganesh to discuss 05/28: Received approval from Mike Reese to move forward with resourcing

## People
Position | Current status | CVS Onboarding status
Tower director - MMCS | Muthu joined CVS engagmenet | ZID complete, laptop received 07/13, setup in progress
Tower director - SMO | Suman joined Cognizant | Completed
Automation director | Profile search is on
SM replacement - Specialty | Nigam Mehta joined | Completed
SM replacement - MMCS | Profile search is on; one discussion scheduled with Ganesh on 07/14
SM - Stability | Krishna joined in Cognizant | ZID complet, laptop is expected to arrive 07/14
SM - Process improvement | Sriram joined CVS engagement | ZID complete, laptop received 07/13, setup in progress

## MSM Pricing Detail (hidden)
s # | Application | Tower | Request date | Disposition | Retirement / Go-live date | Cost credit or increase effective date in the SOW | Y1 - Monthly pricing | 5 year charges (Oct 2020 - Sep 2025) | Approved? | SOW updated? | CR# | Comments
1 | McKesson | Spl |  | Retirement | 2021-02-24 | 2021-04-26 |  |  | Yes | No |  | Swap with Intradiem
2 | Intradiem | Spl |  | New |  | 2021-04-26 |  |  | Yes | No |  | Swap with Mckesson
3 | ACEYUS REPORTING | MMCS | 2021-04-29 | Retirement | 2021-02-24 |  | 9113.14 | 535961.4 | No | No |  | Cognizant agreed to descope the application
4 | CPR+ GENEVAWOODS | Spl | 2021-04-29 | Retirement | Tentative 09/30/2021 |  | 2596.99 | 108196.68 | No | No |  | Cognizant agreed to descope the application
5 | FILE TRACKER - CLIENT ON-BOARDING UI | Adj | 2021-05-10 | Retirement | 2021-09-30 |  | 2596.99 | 108196.68 | No | No |  | Part of the functionality is moving to EWF
6 | FILE TRACKER - XML BUILDER | Adj | 2021-05-10 | Retirement | 2021-07-30 |  | 2596.99 | 108196.68 | No | No |  | Part of the functionality is moving to EWF
7 | MOXIE | MMCS | 2021-04-29 | Retirement | 2021-03-26 |  | 9113.14 | 535961.4 | No | No |  | Cognizant agreed to descope the application
8 | COLA | Adj | 2021-05-10 | Retirement | Tentative 09/30/2021 |  | 2596.99 | 108196.68 | No | No |  | Support is still there, analysis in progress
9 | EWF | Adj | 2021-05-10 | Existing; Functionality consolidation | ? |  | 2596.99 | 108196.68 | No | No |  | 05/14: Functionality of retired applications getting consolidated in EWF. Pricing band require change, Cognizant is working on the procing band proposal.
10 | Letter admin tool | SPL |  | New |  |  |  |  | No | No |  | Waiting for SME input for the estimation

## RAAIID (hidden)
Change log
Applications targetted for retirement in 2021
People changes