## ITPR030519
Project ID | Defect ID | Headline | Applicaton | Severity | State | Release ID | Phase Detected | Date Submitted | Date Completed | Deployment Date
ITPR030519 | DEF0201197953 | NLX split scenario is not working (P2PPAHJ6900) where Allowed line from CXT is fully denied with N6AN NLX rule | A4344-Enterprise Integrations - Claims | Minor | Completed | 02/14/2020 | P5 Integration Test | 12/23/19 12:00 AM | 1/14/20 12:00 AM
ITPR030519 | DEF0201197951 | IIB is not sending correct response in linkage to IIB when claim has both NLX+CXT recommedation | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 Integration Test | 12/23/19 12:00 AM | 1/7/20 12:00 AM
ITPR030519 | DEF0201198005 | Claim Line with CXT On prem frequency rule and other line with NLX Full denial rule - Claim lines are getting wiped from proc | A4344-Enterprise Integrations - Claims | Minor | Completed | 02/14/2020 | P5 Integration Test | 12/26/19 12:00 AM | 1/17/20 12:00 AM
ITPR030519 | DEF0201198003 | IIB sending IC_CASE_LN_ID = 0 for NLX recommeded line (e.g. fully denied line) | A4344-Enterprise Integrations - Claims | Minor | Completed | 02/14/2020 | P5 Integration Test | 12/26/19 12:00 AM | 1/7/20 12:00 AM
ITPR030519 | DEF0201198046 | QuantityLimitExceeded Use case is not working | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 Integration Test | 12/30/19 12:00 AM | 1/14/20 12:00 AM
ITPR030519 | DEF0201198045 | Getting EIE internal error in response from IIB | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 Integration Test | 12/30/19 12:00 AM | 12/31/19 12:00 AM
ITPR030519 | DEF0201198048 | ITPR030519 ¦ Action code not found for C14A rule | A159-Automated Claim Adjudication System | Major | Withdrawn | 02/14/2020 | P5 System & Specialty Test | 12/30/19 12:00 AM | 1/2/20 12:00 AM
ITPR030519 | DEF0201198050 | ITPR030519 ¦ Claim screen doesn't show lines to be paid in case of C014 partial denial | A159-Automated Claim Adjudication System | Major | Withdrawn | 02/14/2020 | P5 System & Specialty Test | 12/30/19 12:00 AM | 1/2/20 12:00 AM
ITPR030519 | DEF0201198093 | ITPR030519 ¦ Member First name is sent incorrectly in xml request | A159-Automated Claim Adjudication System | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/1/20 12:00 AM | 1/8/20 12:00 AM
ITPR030519 | DEF0201198122 | ACAS is not able to send NLX paid feed due to incorrect credentials | A159-Automated Claim Adjudication System | Minor | Completed | 02/14/2020 | P5 Integration Test | 1/2/20 12:00 AM | 1/10/20 12:00 AM
ITPR030519 | DEF0201198239 | ITPR030519 : IC CASE LINE ID = 999999999999 is Invalid, Error generated in Prelim Feed report | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 Integration Test | 1/7/20 12:00 AM | 1/19/20 12:00 AM
ITPR030519 | DEF0201198368 | ITPR030519 ¦ ACAS claim system abend on single line claim | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/9/20 12:00 AM | 1/16/20 12:00 AM
ITPR030519 | DEF0201198379 | ITPR030519 ¦ Incorrect counter on CH Screen for CXT and NLX partial denial on single line | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/9/20 12:00 AM | 1/15/20 12:00 AM
ITPR030519 | DEF0201198380 | ITPR030519 ¦ Paid line not available on claim for CXT and NLX partial denial on single line | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/9/20 12:00 AM | 1/15/20 12:00 AM
ITPR030519 | DEF0201198480 | ITPR030519 ¦ QuantityLimitExceeded rule recommendations from Novologix on multiple expense lines | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 Integration Test | 1/13/20 12:00 AM | 1/15/20 12:00 AM
ITPR030519 | DEF0201198479 | ITPR030519 - CXT denial and NLX frequency claim. | A4344-Enterprise Integrations - Claims | Minor | Completed | 02/14/2020 | P5 Integration Test | 1/13/20 12:00 AM | 1/15/20 12:00 AM
ITPR030519 | DEF0201198481 | ITPR030519 ¦ QuantityLimitExceeded rule recommendations from Novologix on multiple expense lines - Single Case Set | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 Integration Test | 1/13/20 12:00 AM | 1/27/20 12:00 AM
ITPR030519 | DEF0201198544 | ITPR030519 ¦ NLX rule not applied on hospital claims | A4344-Enterprise Integrations - Claims | Minor | Completed | 02/14/2020 | P5 System & Specialty Test | 1/14/20 12:00 AM | 1/23/20 12:00 AM
ITPR030519 | DEF0201198598 | ITPR030519 ¦ Action code not applied for lines denied under NLX rule | A159-Automated Claim Adjudication System | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/16/20 12:00 AM | 1/17/20 12:00 AM
ITPR030519 | DEF0201198619 | Not setting the reverse flag be populated with ‘Y’ | A159-Automated Claim Adjudication System | Minor | Completed | 02/14/2020 | P5 Integration Test | 1/16/20 12:00 AM | 1/17/20 12:00 AM
ITPR030519 | DEF0201198599 | ITPR030519 ¦ ROUTE KEY/AREA INVALID error on claim | A159-Automated Claim Adjudication System | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/16/20 12:00 AM | 1/23/20 12:00 AM
ITPR030519 | DEF0201198680 | NLX :: Issue with IDR file not having 6000 byte record | Vendor Product Third Party Entity | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/17/20 12:00 AM | 1/27/20 12:00 AM
ITPR030519 | DEF0201198786 | ITPR030519 ¦ Abend in ACAS after Monthly limit was fixed | A159-Automated Claim Adjudication System | Minor | Withdrawn | 02/14/2020 | P5 System & Specialty Test | 1/21/20 12:00 AM | 1/29/20 12:00 AM
ITPR030519 | DEF0201198762 | ITPR030520 ¦ Action code not found when N600 adds lines | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/21/20 12:00 AM | 1/28/20 12:00 AM
ITPR030519 | DEF0201198803 | ITPR030519 ¦ CH Screen shows historical data for N600 rule | A4344-Enterprise Integrations - Claims | Minor | Completed | 02/14/2020 | P5 System & Specialty Test | 1/22/20 12:00 AM | 1/27/20 12:00 AM
ITPR030519 | DEF0201198804 | ITPR030519 ¦ NLX rule is not applied when drugs are billed over multiline claim | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/22/20 12:00 AM | 1/23/20 12:00 AM
ITPR030519 | DEF0201198834 | Paid Feed Issue | A159-Automated Claim Adjudication System | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/23/20 12:00 AM | 1/27/20 12:00 AM
ITPR030519 | DEF0201198884 | ITPR030519 ¦ IIB NAP network exclusion not working for non-NAP PO prefix | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/23/20 12:00 AM | 1/30/20 12:00 AM
ITPR030519 | DEF0201198880 | ITPR030519 ¦ NLX Issue ¦ Lines are being sent with duplicate Claim Line Number | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/23/20 12:00 AM | 1/23/20 12:00 AM
ITPR030519 | DEF0201198927 | ITPR030519 ¦ NLX rule not applied on Hospital EDI claim | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/24/20 12:00 AM | 1/28/20 12:00 AM
ITPR030519 | DEF0201198943 | ITPR030519 ¦ Incorrect counters on partial denial | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/24/20 12:00 AM | 1/28/20 12:00 AM
ITPR030519 | DEF0201198958 | ITPR030519 ¦ Exclusion on non-par claims and IIB exclusions not present in ACAS story | A159-Automated Claim Adjudication System | Minor | Completed | 02/14/2020 | P5 System & Specialty Test | 1/26/20 12:00 AM | 1/27/20 12:00 AM
ITPR030519 | DEF0201198975 | ITPR030519 ¦ IIB-CXTSOAP error in ACAS | A4344-Enterprise Integrations - Claims | Major | Withdrawn | 02/14/2020 | P5 System & Specialty Test | 1/27/20 12:00 AM | 1/27/20 12:00 AM
ITPR030519 | DEF0201199168 | ITPR030519 ¦ Paid feed should send Recommendation Applied=N when Reversed Flag=Y | A159-Automated Claim Adjudication System | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 1/31/20 12:00 AM | 2/12/20 12:00 AM
ITPR030519 | DEF0201199211 | ITPR030519 ¦ Conflicting requirements related to Estimator for NLX | A159-Automated Claim Adjudication System | Minor | Completed | 02/14/2020 | P5 System & Specialty Test | 2/3/20 12:00 AM | 2/5/20 12:00 AM
ITPR030519 | DEF0201199244 | UAT: Report being sent to wrong folder, need report sent to correct business folder | A3697-EIE B2B Gateway (batch file framework, Sterl | Minor | Completed | 02/14/2020 | P5 User Acceptance Test | 2/5/20 12:00 AM | 2/6/20 12:00 AM
ITPR030519 | DEF0201199236 | ITPR030519 ¦ NLX rules are not getting applied on the claims **Configuration change on NLX side | Vendor Product Third Party Entity | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 2/5/20 12:00 AM | 2/5/20 12:00 AM
ITPR030519 | DEF0201199235 | ITPR030519 ¦ Rule applied on non-par claim with DOS outside approval window | A159-Automated Claim Adjudication System | Major | Withdrawn | 02/14/2020 | P5 System & Specialty Test | 2/5/20 12:00 AM | 2/5/20 12:00 AM
ITPR030519 | DEF0201199324 | ITPR030519 ¦ Overpayment caused after recycling or manually re-initializing claim that has already been through NLX | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 2/7/20 12:00 AM | 6/18/20 12:00 AM | 6/18/20 12:00 AM
ITPR030519 | DEF0201199323 | ITPR030519 ¦ Overpayment when claim gets through PCA followed by NLX | A159-Automated Claim Adjudication System | Major | Withdrawn | 02/14/2020 | P5 System & Specialty Test | 2/7/20 12:00 AM | 6/2/20 12:00 AM | 5/28/20 12:00 AM
ITPR030519 | DEF0201199379 | ITPR030519 ¦ NLX rules are applied on estimators | A4344-Enterprise Integrations - Claims | Major | Completed | 02/14/2020 | P5 System & Specialty Test | 2/11/20 12:00 AM | 2/12/20 12:00 AM
ITPR030519 | DEF0201199693 | J289NLCX – Novologix Paid Feed | A159-Automated Claim Adjudication System | Minor | Completed | 02/14/2020 | P6 Warranty Period | 2/21/20 12:00 AM | 2/27/20 12:00 AM | 2/27/20 12:00 AM
ITPR030519 | DEF0201199941 | NLX rules are applied on DOS<03/01 | A4344-Enterprise Integrations - Claims | Minor | Completed | 02/14/2020 | P6 Deployment | 3/1/20 12:00 AM | 3/1/20 12:00 AM | 3/1/20 12:00 AM
ITPR030519 | DEF0201199940 | ITPR030519 ¦ Claims are not being sent to NLX for editing | A4344-Enterprise Integrations - Claims | Minor | Completed | 02/14/2020 | P6 Deployment | 3/1/20 12:00 AM | 3/1/20 12:00 AM | 3/1/20 12:00 AM
ITPR030519 | DEF0201201879 | Scenario 1 -IIB not consolidating the duplicate line | A4344-Enterprise Integrations - Claims | Major | Completed | 05/28/2020 | P5 System & Specialty Test | 5/19/20 12:00 AM | 5/28/20 12:00 AM
ITPR030519 | DEF0201201958 | NLX N6AN fired on claim line during 2nd call to CXT/NLX where N600 rule fired initially | A4344-Enterprise Integrations - Claims | Major | Completed | 05/28/2020 | P5 System & Specialty Test | 5/22/20 12:00 AM | 6/8/20 12:00 AM
ITPR030519 | DEF0201201992 | NLX Overpayment DEF Fix ¦¦ “ACTION CODE RULE NOT FOUND IN AC SCREEN FOR LINE:0001-N6AN” with N6AN Rule ID | A4344-Enterprise Integrations - Claims | Major | Completed | 05/28/2020 | P5 System & Specialty Test | 5/26/20 12:00 AM | 6/8/20 12:00 AM

## ITPR040098
Project ID | Defect ID | Headline | Applicaton | Severity | State | Release ID | Phase Detected | Date Submitted | Date Completed | Deployment Date
ITPR040098 | DEF0201201391 | ITPR040098: MCARECCI2 is not getting considered as correct system ID at NLX end | A132-HMO Claims Processing System | Major | Withdrawn | 05/15/2020 | P5 System & Specialty Test | 4/29/20 12:00 AM | 7/31/20 12:00 AM
ITPR040098 | DEF0201201392 | ITPR040098: IIB is passing 14 byte claim no to NLX and at NLX end they can have only 11 byte claim ID. | A2153-ClaimXten (McKesson software) | Major | Completed | 05/15/2020 | P5 System & Specialty Test | 4/29/20 12:00 AM | 5/13/20 12:00 AM
ITPR040098 | DEF0201201563 | ITPR040098_Novologix : Facing abend in claim screen while releasing NLX claim | A132-HMO Claims Processing System | Major | Completed | 05/15/2020 | P5 System & Specialty Test | 5/7/20 12:00 AM | 5/12/20 12:00 AM
ITPR040098 | DEF0201201592 | N600 is getting applied instead of N6AN rule | A132-HMO Claims Processing System | Major | Completed | 05/15/2020 | P5 System & Specialty Test | 5/8/20 12:00 AM | 5/11/20 12:00 AM
ITPR040098 | DEF0201204451 | Splunk Alert: NLX Errors reached the threshold | A4344-Enterprise Integrations - Claims | Minor | Assigned | 08/21/2020 | P6 Warranty Period | 9/11/20 12:00 AM

## ITPR041817
Project ID | Defect ID | Headline | Applicaton | Severity | State | Release ID | Phase Detected | Date Submitted | Date Completed | Deployment Date
ITPR041817 | DEF0201202156 | underpayment : - splitting of lines confirmation needed | A4344-Enterprise Integrations - Claims | Major | Completed | 06/18/2020 | P5 System & Specialty Test | 6/4/20 12:00 AM | 6/5/20 12:00 AM
ITPR041817 | DEF0201202148 | facing abend | A4344-Enterprise Integrations - Claims | Major | Completed | 06/18/2020 | P5 System & Specialty Test | 6/4/20 12:00 AM | 6/4/20 12:00 AM
ITPR041817 | DEF0201202150 | [Underpayment] Lines in Claim and CH screen not in sync after recycle transaction ¦ | A4344-Enterprise Integrations - Claims | Major | Completed | 06/18/2020 | P5 System & Specialty Test | 6/4/20 12:00 AM | 6/10/20 12:00 AM
ITPR041817 | DEF0201202199 | [Overpayment] 90 units getting overpaid as N600 rule not fired after 2nd transaction to CXT | A4344-Enterprise Integrations - Claims | Major | Completed | 06/18/2020 | P5 System & Specialty Test | 6/5/20 12:00 AM | 6/8/20 12:00 AM
ITPR041817 | DEF0201202185 | [Overpayment] 100 units getting overpaid for line with proc Q5104 ¦¦ Line J1745 present in CH screen with RPTCD as ' -PN' an | A4344-Enterprise Integrations - Claims | Major | Completed | 06/18/2020 | P5 System & Specialty Test | 6/5/20 12:00 AM | 6/10/20 12:00 AM
ITPR041817 | DEF0201202233 | [Overpayment] 180 units getting overpaid for same proc billed on two different DOS | A4344-Enterprise Integrations - Claims | Major | Completed | 06/18/2020 | P5 System & Specialty Test | 6/9/20 12:00 AM | 6/10/20 12:00 AM
ITPR041817 | DEF0201202276 | [Overpayment] 75 units getting overpaid for same proc billed on two different DOS with units exceeded only on DOS1 | A4344-Enterprise Integrations - Claims | Major | Completed | 06/18/2020 | P5 System & Specialty Test | 6/10/20 12:00 AM | 6/10/20 12:00 AM
ITPR041817 | DEF0201202280 | underpayment occuring after fix for DEF0201202150 | A4344-Enterprise Integrations - Claims | Major | Completed | 06/18/2020 | P5 System & Specialty Test | 6/10/20 12:00 AM | 6/10/20 12:00 AM
ITPR041817 | DEF0201202278 | C14A should deny units first, then NLX can deny additional units | A4344-Enterprise Integrations - Claims | Major | Completed | 06/18/2020 | P5 System & Specialty Test | 6/10/20 12:00 AM | 6/15/20 12:00 AM
ITPR041817 | DEF0201202327 | Overpayment caused due to date mismatch in CH and Claim screens ¦¦ J2182 billed on 2 different DOS ¦¦ N6DX rule testing | A4344-Enterprise Integrations - Claims | Major | Completed | 06/18/2020 | P5 System & Specialty Test | 6/12/20 12:00 AM | 6/15/20 12:00 AM
ITPR041817 | DEF0201202329 | Claim lines are getting omitted during 2nd transaction ¦¦ Additional line present in CH screen with RPTCD as ' -PN | A4344-Enterprise Integrations - Claims | Major | Completed | 06/18/2020 | P5 System & Specialty Test | 6/12/20 12:00 AM | 6/17/20 12:00 AM
ITPR041817 | DEF0201202354 | [Regression] 100 units Underpayment ¦¦ N6DX rule not fired after 2nd transaction ¦¦ Claim lines got denied by C040 CXT On pre | A4344-Enterprise Integrations - Claims | Major | Completed | 06/18/2020 | P5 System & Specialty Test | 6/15/20 12:00 AM | 6/17/20 12:00 AM
ITPR041817 | DEF0201202406 | Error message 'PLEASE CORRECT HIGHLIGHTED FIELDS - CTR' on claim screen | A4344-Enterprise Integrations - Claims | Major | Completed | 06/18/2020 | P5 System & Specialty Test | 6/17/20 12:00 AM | 6/17/20 12:00 AM
ITPR041817 | DEF0201202452 | NLX CXT rule is being returned on a newly created line with zero dollars | A4344-Enterprise Integrations - Claims | Minor | Completed | 06/18/2020 | P6 Deployment | 6/18/20 12:00 AM | 6/23/20 12:00 AM | 6/22/20 12:00 AM
ITPR041817 | DEF0201202446 | On recall no rules showing in CH, on initilization its coming on CH | A4344-Enterprise Integrations - Claims | Major | Pending_Warranty | 06/18/2020 | P5 System & Specialty Test | 6/18/20 12:00 AM
ITPR041817 | DEF0201203098 | ITPR041817 ¦ Paid feed did not include all modifier codes | A159-Automated Claim Adjudication System | Major | Completed | 08/14/2020 | P5 System & Specialty Test | 7/8/20 12:00 AM | 7/14/20 12:00 AM
ITPR041817 | DEF0201203281 | ITPR041817 ¦ Second modifier is incorrect in Paid feed | A159-Automated Claim Adjudication System | Minor | Completed | 08/14/2020 | P5 System & Specialty Test | 7/14/20 12:00 AM | 7/16/20 12:00 AM
ITPR041817 | DEF0201203475 | ITPR041817 ¦ Edited Procedure Code and Units populated are blank on auto-segmented claim | A159-Automated Claim Adjudication System | Minor | Completed | 08/14/2020 | P5 System & Specialty Test | 7/20/20 12:00 AM | 7/21/20 12:00 AM
ITPR041817 | DEF0201200702 | UAT logged defect Post Release - Edit - UNSUPPORTED UNITS PRECERTED – MANUALLY CALC UNITS TO ALLW and W91 denial | A159-Automated Claim Adjudication System | Minor | Deferred | 03/26/2020 | P6 Warranty Period | 7/28/20 12:00 AM |  | 6/15/20 12:00 AM
ITPR041817 | DEF0201204182 | ITPR041817 Novologix (Sept'20-09/10) - Facing abend while filing hospital claim. | A159-Automated Claim Adjudication System | Minor | Completed | 09/14/2020 | P5 Integration Test | 8/26/20 12:00 AM | 9/2/20 12:00 AM
ITPR041817 | DEF0201204179 | ITPR041817: Include 15 bytes for Member ID for exclusion criteria consideration for Novologix | A4344-Enterprise Integrations - Claims | Minor | Completed | 09/14/2020 | P5 System & Specialty Test | 8/26/20 12:00 AM | 9/2/20 12:00 AM
ITPR041817 | DEF0201204181 | ITPR041817: C0RS rule is getting suppressed irrespective of the claim expense line is eligible for NLX or not | A4344-Enterprise Integrations - Claims | Major | Completed | 09/14/2020 | P5 System & Specialty Test | 8/26/20 12:00 AM | 9/4/20 12:00 AM
ITPR041817 | DEF0201204195 | ITPR041817- C2DF rule is getting suppressed irrespective of the claim expense line is eligible for NLX or not | A4344-Enterprise Integrations - Claims | Minor | Completed | 09/14/2020 | P5 System & Specialty Test | 8/27/20 12:00 AM | 9/4/20 12:00 AM
ITPR041817 | DEF0201204267 | ITPR041817: [Overpayment] N6DX RULE- 90 units getting overpaid for Diff Units billed on two same DOS | A4344-Enterprise Integrations - Claims | Major | Completed | 09/14/2020 | P5 System & Specialty Test | 9/1/20 12:00 AM | 9/4/20 12:00 AM
ITPR041817 | DEF0201204264 | ITPR041817: QA01 : CXT Timeout issue | A4344-Enterprise Integrations - Claims | Major | Completed | 09/14/2020 | P5 System & Specialty Test | 9/1/20 12:00 AM | 9/4/20 12:00 AM
ITPR041817 | DEF0201204266 | ITPR041817: [Overpayment] N600 RULE- 299 units getting overpaid and (CXT, NLX) Rule not getting applied on 2nd Instance | A4344-Enterprise Integrations - Claims | Major | Completed | 09/14/2020 | P5 System & Specialty Test | 9/1/20 12:00 AM | 9/4/20 12:00 AM
ITPR041817 | DEF0201204339 | ITPR041817: [Overpayment] 10 units getting overpaid and NLX Rule not getting applied | A4344-Enterprise Integrations - Claims | Major | Completed | 09/14/2020 | P5 System & Specialty Test | 9/4/20 12:00 AM | 9/8/20 12:00 AM
ITPR041817 | DEF0201204368 | ITPR041817 (Duplicate Line):New edit 'ACTION CODE RULE NOT FOUND IN AC SCREEN FOR LINE:0003-100'& N600 is not getting applied | A4344-Enterprise Integrations - Claims | Minor | Completed | 09/14/2020 | P5 System & Specialty Test | 9/8/20 12:00 AM | 9/14/20 12:00 AM
ITPR041817 | DEF0201204365 | ITPR041817-“ACTION CODE RULE NOT FOUND IN AC SCREEN FOR LINE:0003-C14A" is getting populated on duplicate claim | A159-Automated Claim Adjudication System | Major | Completed | 09/14/2020 | P5 System & Specialty Test | 9/8/20 12:00 AM | 9/14/20 12:00 AM
ITPR041817 | DEF0201204376 | ITPR041817-C4EI rule is not getting retained on claim after applying SL AO override | A159-Automated Claim Adjudication System | Minor | Completed | 09/14/2020 | P5 System & Specialty Test | 9/8/20 12:00 AM | 9/9/20 12:00 AM
ITPR041817 | DEF0201204351 | Y Display shows lines are incorrectly denying 124MAX BEN PD | A159-Automated Claim Adjudication System | Minor | Withdrawn | 09/14/2020 | P5 User Acceptance Test | 9/14/20 12:00 AM | 9/14/20 12:00 AM

## ITPR041816
Project ID | Defect ID | Headline | Applicaton | Severity | State | Release ID | Phase Detected | Date Submitted | Date Completed | Deployment Date
ITPR041816 | DEF0201203127 | ITPR041816 ¦ NLX Paid feed also carries lines with CXT cloud rules | A159-Automated Claim Adjudication System | Major | Completed | 08/14/2020 | P5 System & Specialty Test | 7/8/20 12:00 AM | 7/9/20 12:00 AM
ITPR041816 | DEF0201203439 | ITPR041816 ¦ NL override not retained on claim line after CXT is re-invoked | A159-Automated Claim Adjudication System | Major | Pending_Warranty | 08/14/2020 | P5 System & Specialty Test | 7/20/20 12:00 AM |  | 11/13/20 12:00 AM
ITPR041816 | DEF0201203512 | ITPR041816 ¦ N600 rule not applied on Provider estimate | A4344-Enterprise Integrations - Claims | Minor | Withdrawn | 08/14/2020 | P5 System & Specialty Test | 7/22/20 12:00 AM | 7/24/20 12:00 AM
ITPR041816 | DEF0201203612 | ITPR041816 ¦ Claim with NL AO are going into recycle error | A159-Automated Claim Adjudication System | Minor | Withdrawn | 08/14/2020 | P5 System & Specialty Test | 7/27/20 12:00 AM | 7/30/20 12:00 AM
ITPR041816 | DEF0201203678 | ITPR041816 ¦ ACAS receives error from NLX | Vendor Product Third Party Entity | Major | Completed | 08/14/2020 | P5 System & Specialty Test | 7/29/20 12:00 AM | 7/30/20 12:00 AM
ITPR041816 | DEF0201203758 | ITPR041816 ¦ CXT rule was not applied when quntities were billed on 3(or more) separate lines | A4344-Enterprise Integrations - Claims | Major | Completed | 08/14/2020 | P5 System & Specialty Test | 7/31/20 12:00 AM | 9/14/20 12:00 AM | 9/14/20 12:00 AM
ITPR041816 | DEF0201204583 | ITPR041816: NLX rule getting applied on Members where NLX Auth is not setup | A159-Automated Claim Adjudication System | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 9/21/20 12:00 AM | 10/6/20 12:00 AM
ITPR041816 | DEF0201204766 | ITPR041816:: Rule not firing due to certainty of review | A3853-ClaimXten 5.2 (McKesson software) | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 9/29/20 12:00 AM | 10/6/20 12:00 AM
ITPR041816 | DEF0201204763 | ITPR041816:: Dictionary change for NXX rule to N6CX | A3853-ClaimXten 5.2 (McKesson software) | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 9/29/20 12:00 AM | 10/6/20 12:00 AM
ITPR041816 | DEF0201204832 | ITPR041816: Issue regarding CXT5 error on NLX claims | A159-Automated Claim Adjudication System | Major | Completed | 11/13/2020 | P5 System & Specialty Test | 9/30/20 12:00 AM | 10/6/20 12:00 AM
ITPR041816 | DEF0201204813 | ITPR041816::: ‘ACTION CODE RULE NOT FOUND IN AC SCREEN FOR LINE:0002-N600’ edit is getting populated | A159-Automated Claim Adjudication System | Major | Completed | 11/13/2020 | P5 System & Specialty Test | 9/30/20 12:00 AM | 10/6/20 12:00 AM
ITPR041816 | DEF0201204917 | ITPR041816 : Recommendation received date is not getting applied correctly- CLAIM LAB and CCES_NLX_DTL | A159-Automated Claim Adjudication System | Major | Withdrawn | 11/13/2020 | P5 System & Specialty Test | 10/6/20 12:00 AM | 10/9/20 12:00 AM
ITPR041816 | DEF0201204914 | ITPR041816 - Novologix: NLX Claims not getting picked in MQ File and NLX Paid Feed | A159-Automated Claim Adjudication System | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/6/20 12:00 AM | 10/9/20 12:00 AM
ITPR041816 | DEF0201204915 | ITPR041816: Generic issue: ACTION CODE RULE NOT FOUND IN AC SCREEN FOR LINE: - C48N rule | A159-Automated Claim Adjudication System | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/6/20 12:00 AM | 10/9/20 12:00 AM
ITPR041816 | DEF0201204918 | ITPR041816: Incorrect NLX rules are getting applied on the claims- N6DX, N6DA, N600 rules tested | A159-Automated Claim Adjudication System | Major | Completed | 11/13/2020 | P5 System & Specialty Test | 10/6/20 12:00 AM | 10/13/20 12:00 AM
ITPR041816 | DEF0201204971 | ITPR041816: N600 not hit on the claim with D6 Response from NLX- future dated claim | A159-Automated Claim Adjudication System | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/8/20 12:00 AM | 10/15/20 12:00 AM
ITPR041816 | DEF0201205037 | ITPR041816::: NLX rules not getting applied on claims | A159-Automated Claim Adjudication System | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/12/20 12:00 AM | 10/13/20 12:00 AM
ITPR041816 | DEF0201205073 | ITPR041816(story:237369):NLX recommendation getting applied on opted out members. | A159-Automated Claim Adjudication System | Major | Completed | 11/13/2020 | P5 System & Specialty Test | 10/13/20 12:00 AM | 10/17/20 12:00 AM
ITPR041816 | DEF0201205074 | ITPR041816(Story-238117) NLX rule is getting applied on SCCU claims | A159-Automated Claim Adjudication System | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/13/20 12:00 AM | 10/20/20 12:00 AM
ITPR041816 | DEF0201205171 | ITPR041816:(Story-243838)Sept'20 regression: NLX rule not applied by suppressing C2DF duplicate lines | A159-Automated Claim Adjudication System | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/17/20 12:00 AM | 10/23/20 12:00 AM
ITPR041816 | DEF0201205170 | ITPR041816 -C0RS rule is getting applied on NLX claim - Regression from Sept'20 | A159-Automated Claim Adjudication System | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/17/20 12:00 AM | 10/22/20 12:00 AM
ITPR041816 | DEF0201205206 | System not retaining original NLX recommendations on recalled claim | A159-Automated Claim Adjudication System | Minor | Withdrawn | 11/13/2020 | P5 User Acceptance Test | 10/19/20 12:00 AM | 10/20/20 12:00 AM
ITPR041816 | DEF0201205217 | ITPR041816 Story Id:- 237863: NXL recommendation Indicator populated as N instead of Y for CCH1 | A159-Automated Claim Adjudication System | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/20/20 12:00 AM | 10/22/20 12:00 AM
ITPR041816 | DEF0201205262 | ITPR041816(story:237369):OPT IN/OPT OUT fields are getting populated incorrectly for case rate scenarios- Update Requriement | A159-Automated Claim Adjudication System | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/21/20 12:00 AM | 10/21/20 12:00 AM
ITPR041816 | DEF0201205307 | ITPR041816 Story Id :- 237853 :: NLX rules N600,N6DX and N6DA is not applying on CCH1 claims | A159-Automated Claim Adjudication System | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/23/20 12:00 AM | 10/26/20 12:00 AM
ITPR041816 | DEF0201205308 | ITPR041816: Issue regarding claims lines expanding and collapsing - rules getting applied on CH Screen | A3853-ClaimXten 5.2 (McKesson software) | Minor | Pending_Warranty | 11/13/2020 | P5 System & Specialty Test | 10/23/20 12:00 AM |  | 2/12/21 12:00 AM
ITPR041816 | DEF0201205306 | ITPR041816(STORY:243838):SEPT '20' REGRESSION-MEMBER ON EXCLUSION LIST- NLX rules fired | A3853-ClaimXten 5.2 (McKesson software) | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/23/20 12:00 AM | 10/30/20 12:00 AM
ITPR041816 | DEF0201205335 | NLX and CCES rules are firing but lines are not denying | A159-Automated Claim Adjudication System | Minor | Withdrawn | 11/13/2020 | P5 User Acceptance Test | 10/26/20 12:00 AM | 10/28/20 12:00 AM
ITPR041816 | DEF0201205364 | ITPR041816: Issue regarding estimates not returning NLX rules | A159-Automated Claim Adjudication System | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/27/20 12:00 AM | 10/30/20 12:00 AM
ITPR041816 | DEF0201205391 | ITPR041816(Story-238117)-NLX rule not getting applied after internal pricing due to lesser of logic on VIANT claim | A159-Automated Claim Adjudication System | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/28/20 12:00 AM | 11/3/20 12:00 AM
ITPR041816 | DEF0201205400 | ITPR041816(story:237855) :Need confirmation regarding NLX Rec Indicator -requirements updated | A159-Automated Claim Adjudication System | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/28/20 12:00 AM | 10/28/20 12:00 AM
ITPR041816 | DEF0201205403 | Electronic facility claim dropped to processor is not retaining NLX recommendation | A159-Automated Claim Adjudication System | Minor | Withdrawn | 11/13/2020 | P5 User Acceptance Test | 10/28/20 12:00 AM | 11/5/20 12:00 AM
ITPR041816 | DEF0201205414 | ITPR041816 Story Id :- 237853 :: NLX rules are not bypassing after providing NL AO override | A3853-ClaimXten 5.2 (McKesson software) | Minor | Completed | 11/13/2020 | P5 System & Specialty Test | 10/29/20 12:00 AM | 11/6/20 12:00 AM
ITPR041816 | DEF0201205266 | ITPR041816 NDC code for J3490 - no NLX rule applied - CXT NLX Mapping issue | A3853-ClaimXten 5.2 (McKesson software) | Major | Pending_Warranty | 11/13/2020 | P5 System & Specialty Test | 11/6/20 12:00 AM |  | 2/12/21 12:00 AM
ITPR041816 | DEF0201205750 | Novologix - CXT Integration: Error returned from CXT to Claims systems for certain combinations of NLX responses | A2153-ClaimXten (McKesson software) | Minor | Completed | 11/13/2020 | P6 Deployment | 11/15/20 12:00 AM | 12/7/20 12:00 AM | 11/22/20 12:00 AM

## ITPR042956
Project ID | Defect ID | Headline | Applicaton | Severity | State | Release ID | Phase Detected | Date Submitted | Date Completed | Deployment Date
ITPR042956 | DEF0201204819 | Novologix rule not getting applied for HMO claims in QA path 2 | A132-HMO Claims Processing System | Major | Completed | 11/13/2020 | P5 System & Specialty Test | 9/30/20 12:00 AM | 10/12/20 12:00 AM
ITPR042956 | DEF0201205303 | ITPR042956: HMO NDC INfO screen not getting initialized when proc code is getting changed | A132-HMO Claims Processing System | Major | Deferred | 11/13/2020 | P5 System & Specialty Test | 10/23/20 12:00 AM